## Fee Payment
Backend Backlog - Fee Payment
Sl No. | Story ID | Sprint No. | Feature | Phase | User Story | Task | Hours required | Delivery Date(Expected) | Delivered Date | Delivery Status | PMO Remarks | Resource | Backend Dev Remarks | Admin Changes | API changes | Dev Changes needed/Dependent
1 | 0.001 |  | Payment from application is not reflecting in SMS | Phase 1 |  |  |  | 16th June | 17th June | Completed | To be done immediately, facing challenges | Arijit |  | No | Yes | Yes
2 | 0.002 |  | Success Icon not working (loading), Success Parameter value coming as Null | Phase 1 |  |  |  | 16th June | 17th June | Completed | To be done immediately | Arijit |  | No | Yes | Yes
3 | 0.003 |  | Transaction history to be logged for Payment Failure scenarios | Phase 1 |  |  | 4hours | 16th June | 17th June | Completed | Old data migration logic to be discussed between SK and Farooque | Sahidur |  | Yes | Yes | No
4 | 0.004 |  | Transaction history to be logged for Payment Failure scenarios | Phase 1 |  |  | 2hours | 16th June | 17th June | Completed |  | Arijit |  | Yes | Yes | No
5 | 0.005 |  | Generate receipts Invoice is pending(on clicking Download PDF) | Phase 1 |  |  | 4hours | 16th June | 23rd June | Completed | Delayed due to Fee payment bug fixes | Arijit |  | No | Yes | No
6 | 0.006 |  | Payment from Backend is not reflecting in Transaction History | Phase 1 |  |  |  | 19th June | 24th June | Completed |  | Arijit |  | No | Yes | No
7 | 0.007 |  | Clicking on Download icon against each transaction, it shows 400 in the footer | Phase 1 | [5 empty] | Completed | due to old data not avaiable in PP Server | Arijit | To be tested PP image data is now updated with prod. | No | Yes | No
8 | 0.008 |  | For Individual student also Transaction history currently shows old data of all students | Phase 1 |  |  |  | 30th June | 28th June | Completed
9 | 0.009 |  | Admin screen needed > Payment Log trail status check > Requery and Reconcilation for Online Transactions | Phase 2 |  |  |  | 7th July |  | Pending | To be done post Result module (24th July)
10 | 0.01 |  | Brand ID wise API changes needed (token) | Phase 1 |  |  |  | 28th July |  | Completed | [5 empty] | Yes
11 | 0.011 | Sprint 2 | Change request on Fine Collection (Eduqfix) of AIS | Phase 1 | If any students fee due then late fine amount need to show in apps > Late Fee Payment (FIne) amount as part of Total Fee Component. Note: Even though it's an Adhoc Payment, we need to show it as part of Fee Component only |  |  |  |  | In Progress |  | Sh
12 | 0.012 | Sprint 2 | Change request on Fine Collection (Eduqfix) of AWS | Phase 1 | Same as above |  |  |  |  | In Progress
13 | 0.013 |  | Revised Fees Structure for AWS for Session 24- 25 for Trasnport Fee | Ad Hoc | 1. Create course structure, without course batches will be not possible to create. 2. To accomodate below: a. Revised Transport Fee b. Final Fees Structure for session 24-25 |  |  |  |  | On Hold | As per Susmita: Backend Procedure i have partially created at the time when it was 1st time came for Insert and Update in urgent basis.Executed result running more than 6month now with out report Bug To be done at the begining of Academic year as confirmd by Samarjit Das. School will notify. | Tridip
14 | 0.014 |  | On Transaction Histroy > Fee Payment Receipt for 2nd time download, system shall show Duplicate Record with Watermark | Phase 1 | [5 empty] | On Hold | [5 empty] | Yes
15 | 0.015 |  | Report Generation for comparison of Amount Paid by Parents Vs Amount actually received | Phase 2 | [5 empty] | Not Started
16 | 0.016 |  | Fee Dashboard with Day’s Collection, Dues-Receipts, etc. | Phase 2 | [5 empty] | Not Started
17 | 0.017 | SPRINT 1 | On Transaction Histroy > Fee Payment Receipt, if No Payment Receipt is available, upon clicking system shall not show blank page, instead provide message ''Please contact Admin'' | Phase 1 | [5 empty] | On Hold

## Gatepass
Backend Backlog- Gate Pass
Sl No. | Story ID | Sprint No. | Feature | Phase | User Story | Task | Hours required | Delivery Date(Expected) | Delivered Date | Delivery Status | PMO Remarks | Resource | Backend Dev Remarks | Admin Changes | API changes | Dev Changes needed/Dependent
1 | 1.001 |  | Add/Edit/Delete Guardian API | Phase 1 |  |  | 0.5hours | 20th June | 21st June | Completed | add /edit /delete done | Arijit | add /edit /delete done | No | Yes | Yes
2 | 1.002 |  | GatePass Approve/Cancel after Approve API | Phase 1 |  |  | 4hrs | 20th June | 21st June | Completed | Approve API shared on 19th June Implementation done To be tested on PP | Bivash |  | Yes | Yes | Yes
3 | 1.003 |  | GatePass Approve/Cancel after Approve API | Phase 1 | API changes simultaneous If for 2 children, bus drop off gets cancelled, separately gatepass time to be captured in API |  | 3hours | 20th June | 21st June | Completed | Delayed by 1 day as SMS Server is down (20th June) To be tested on PP | Arijit |  | Yes | Yes | Yes
4 | 1.004 |  | In case of Schedule Activity, Gate Pass to be created automatically: (API logic to be updated) | Phase 1 | If from Schedule Activity, Gate pass is scheduled, no cancel option to be given for Pending status but how to track whether Gatepass is created from Bus Module or Gatepass module |  | 1hour | 20th June | 20th June | Completed | Delayed by 1 day as SMS Server is down | Arijit | IsScheduleActivity flag added to identify that the gate is created from schedule activity | No | Yes | Yes
5 | 1.005 |  | Gatepass validation logic <SK> | Phase 1 | Time Validation to be controlled via Backend Configuration: (Entity Id, Module Id, Activity, Time) a. Bus Tracking > Schedule Activity: Create / Cancel / Approve. b. Gatepass Module: Create/ Cancel / Approve. |  | 5hours | 20th June | 21st June | Completed | Delayed by 1 day as SMS Server is down | Sahidur |  | No | Yes | Yes
6 | 1.006 |  | After Gatepass validation logic validation API New | Phase 1 | . Time Validation to be controlled via Backend Configuration: (Entity Id, Module Id, Activity, Time) a. Bus Tracking > Schedule Activity: Create / Cancel / Approve. b. Gatepass Module: Create/ Cancel / Approve. |  | 3hours | 21st June | 21st June | Completed | Delayed by 1 day as SMS Server is down | Arijit |  | No | Yes | Yes
7 | 1.007 |  | 1. Add a Guardian DB logic integration 2. API logic integration for both below Use cases: | Phase 1 | i. Gate Pass Status Pending > User cancels- Date consideration for Time Bound validation (Time To and From fields to be included from backend) ii. Gate Pass Status Approved > User Raise a Request |  | NA | 5th June | 7th June | Completed |  | Arijit |  | No | Yes | Yes
8 | 1.008 |  | Gate pass date range validation, schedule activity API | Phase 1 |  |  | NA | 8th June | 8th June | Completed |  | Arijit |  | No | Yes | Yes
9 | 1.009 |  | Login Flow | Phase 1 |  |  |  | 5th June | 6th June | Completed |  | Arijit |  | No | Yes | Yes
10 | 1.01 |  | If 2 children bus drop off gets cancelled, separately gatepass time to be captured for API - Edit and Delete | Phase 1 |  |  |  | TBD |  | Completed |  | Arijit | Api providede for add edit and delete
11 | 1.011 |  | Gate pass check out key After checkout from parent app- its needs to define over Admin | Phase 1 | [5 empty] | Completed |  | Arijit
12 | 1.012 |  | Delete option for Pending Unavailability Request | Phase 1 | Need to capture reason selected for Delete Gatepass |  |  |  |  | Pending
13 | 1.013 |  |  | Phase 1 | Support Master reason list (for admin) to select Delete Reason |  |  |  |  | Pending

## Guard (hidden)
Backend Backlog - Guard
Sl No. | Story ID | Sprint No. | Feature | Phase | User Story | Task | Hours required | Delivery Date(Expected) | Delivered Date | Delivery Status | PMO Remarks | Resource | Backend Dev Remarks | Admin Changes | API changes | Dev Changes needed/Dependent
1 | 3.001 |  | Guard Role in SMS implementation | Phase 1 |  |  | 3hours |  | 16th June | Completed |  | Susmita |  |  |  | No
2 | 3.002 |  | Login API | Phase 1 |  |  | 4hours |  | 17th June | Completed |  | Susmita |  |  |  | Yes
3 | 3.003 |  | Otp Verification and API and Token Generation | Phase 1 |  |  | 3hours |  | 3rd July | Completed |  | Susmita |  |  |  | Yes
4 | 3.004 |  | After login API | Phase 1 | i. Guard Profile ii. Approved Gate Pass list |  | 3hours | 20th June | 3rd July | Completed | Expired' status to be added GatePass listing in Parent Login and Dev UI | Susmita |  |  |  | Yes
5 | 3.005 |  | Gate Pass QR scan API and Update in SMS | Phase 1 | i. Invalid QR check |  | 6hours | TBD | 27th June | Completed |  | Susmita |  |  |  | Yes
6 | 3.006 |  | 1. Gate pass details json, i.e. studentImage & pickupPersonImage. | Phase 1 |  |  |  |  | 7th July | Completed |  | Susmita |  |  |  | Yes

## Login
Backend Backlog - Login
Sl No. | Story ID | Sprint No. | Feature | Phase | Resource | User Story | Task | Hours required | Delivery Date(Expected) | Delivered Date | Delivery Status | PMO Remarks | Backend Dev Remarks | Admin Changes | API changes | Dev Changes needed/Dependent
1 | 5.001 |  | OTP Validation [APP] | Phase 1 |  |  |  | 3 hours | 7th July | 11th July | Completed
2 | 5.002 |  | OTP auto read [APP] | Phase 1 |  |  |  |  | 7th July | 11th July | Completed
3 | 5.003 |  | Token Flow SMS to Buzzed | Phase 1 |  |  |  | 4hours | 7th July | 11th July | Completed
4 | 5.004 |  | Re OTP | Phase 1 |  |  |  | 3hours | 7th July | 11th July | Completed
5 | 5.005 |  | Parent Login Validation | Phase 1 |  |  |  | 3hours | 7th July | 11th July | Completed
6 | 5.006 |  | Buzzed , SMS, New UI admin Login Flow linking multiple server and token | Phase 1 |  |  |  | TBD | 7th July | 25th July | Completed | Will take it further after POC
7 | 5.007 |  | Production Deployment Old to New login linkup | Phase 1 |  |  |  |  | 7th July |  | Pending | Will take it further after POC
8 | 5.008 |  | Biometric Login | Phase 2 | [6 empty] | Not Started

## Dashboard (hidden)
Backend Backlog - Dashboard
Sl No. | Story ID | Sprint No. | Feature | Phase | User Story | Task | Hours required | Delivery Date(Expected) | Delivered Date | Delivery Status | PMO Remarks | Resource | Backend Dev Remarks | Admin Changes | API changes | Dev Changes needed/Dependent
1 | 6.001 |  | Floating bars for Announcement | Phase 1 |  |  |  | 12th June | 12th June | Completed |  |  |  |  | Yes
2 | 6.002 |  | Date and Time Announement Dashboard | Phase 1 |  |  |  | 16th June |  | Completed |  |  |  |  | Yes

## Notifications
Backend Backlog - Notifications
Sl No. | Story ID | Sprint No. | Feature | Phase | Resource | User Story | Task | Hours required | Delivery Date(Expected) | Delivered Date | Delivery Status | PMO Remarks | Backend Dev Remarks | Admin Changes | API changes | Dev Changes needed/Dependent
1 | 4.001 |  | Notification Setup | Phase 1 | Sahidur/Arijit | "Annoucement: 1. Template creation 2. Setup - Scheduled /Instant Configuration: 2a Define Group of users to send Notification: i. Student a. Class/Batch/Individual ii. Teaching Staff iii. All (Teacher + Student) 2b. Define Flag: Whether to display under Event/ Announcement /Calendar tag agaisnt unique identifier 2c.. Define Notification Type as: i. Email - To be either pre-defined or instant, Text/attachment ii. SMS - To be based on system pre-defined template, only in text mode iii. Push Notifications (Firebase) a. To be either pre-defined or instant, Text/image link B. Define Email template: Subject, Body, Message type" |  | 20hours | 30th June |  | Completed | Buffer kept for Bug fixes for Gatepass, Result modules |  | Yes | Yes | TBD
2 | 4.002 |  | Notification Setup | Phase 1 |  | SMS templtate Tridip Chatterjee, API Process, Template Approval |  |  |  |  | Completed
3 | 4.003 |  | Notification Sent Mechanism | Phase 1 | Sahidur/Arijit | Notification Sent Mechanism |  | 4hours | 30th June |  | Completed |  |  | Yes | Yes | TBD
4 | 4.004 | Sprint No.1 | Notifications | Phase 1 | Susmita | Notifications Report Status | 1. Listing Status for SMS 2. Listing Status for Email 3. Summary Report Over ALL | 16 hours | TBD |  | In Progress
5 | 4.005 | Sprint No.1 | Notifications | Phase 1 | Susmita | Notification Sent Mechanism (Push SMS pending via SSIS) based on credentials | Configuration | 4 hours |  |  | On Hold (per susmita) | ALOK needs to speak with trideep
6 | 4.006 | Sprint No.1 | Notifications | Phase 1 | Susmita | Close User group email activity, Notification filtration, email smtp & messg configuration, personalized email | 1.Modify the Student Group filter structure for feasible searching of Student (Done) 2. Make the All Fetch Dynamic by Brand(For now on ly AIS is staticaly setup)(done) 3. Upload image send the group of students instance push notifications.(done) 4. Multiple attachment group of students through email ( Email, Text shall be brand and provider specific (DB level changes needed) Email service provider - SES, SMTP, POP3 ) 5. Role Management | 4 + 4 + 6 + 4(need to increase to 32) + 4 |  |  | In Progress | Batch, class, individual issues as not able to send
7 | 4.007 |  | Notifications | Phase 1 | Susmita | Intimation on Fee Payment via Email and SMS |  |  |  |  | Pending
8 | 4.008 |  | Notifications | Phase 1 | Susmita | Alert Mail to Management for School Attendance/ Absentees SMS |  |  |  |  | Pending
9 | 4.009 |  | Notifications | Phase 1 | Susmita | Auto Overdue Fee Reminders |  |  |  |  | Pending
10 | 4.01 |  | Notifications | Phase 1 | Susmita | Post Fee Payment, SMS to be sent to Parents |  |  |  |  | Pending
11 | 4.011 |  | Notifications | Phase 2 |  | Push Notifications with Image |  |  |  |  | Not Started
12 | 4.012 |  | Notifications | Phase 2 |  | Notifications via Scheduling |  |  |  |  | Not Started | Currently Only Instant Notifications are working
11 | 4.011 |  | Notifications | Phase 1 |  | Email, Text shall be brand and provider specific (DB level changes needed) | Email service provider - SES, SMTP, POP3 Text message service provider - Twilio, Telesign etc (This is added per discussion with Farooque Sir and Susmita) |  |  |  | Pending
12 | 4.012 |  | Notifications | Phase 1 |  | Support 3rd party plug and play integrations for sending notifications for School App and Parent App | Smart integration Via external clients with Plug and Play (for communication between school, teacher, parent/students (example - whatsapp, Gupshup) |  |  |  | Pending
13
14
15
12 | 4.013 |  | Notifications | Phase 1 |  | Email notification Templates | Sample Templates have been shared with Susmita |  |  |  | Pending

## Bus Tracking
Backend Backlog - Bus Tracking
Sl No. | Story ID | Sprint No. | Feature | Phase | Resource | User Story | Task | Hours required | Daily hour allocation | Working Date Allocation | Delivery Date(Expected) | Delivered Date | Delivery Status | PMO Remarks | Additional Comments
1 | 10.001 |  | Dashboard should be date wise, and time slot wise(8:00 am,10:00 am,11:45 pm,01:45 pm ,03:30 pm )-Total trip, Running trip, End trip, Pending trips ). So that it can be easier to find out slot wise ,how many Total trips, running trips and end trips, pending trips. | Phase 1 | Bivash |  |  |  | 1 day |  |  | 18th Aug 2023 | Completed
2 | 10.002 |  | If due to some reason , attendant unable to login into app but he picked all students up then what to do at the time of drop | Phase 1 | Bivash | [6 empty] | 18th Aug 2023 | Completed
3 | 10.003 |  | If attendant picked all students up but due to some reason attendant unable to login into app while dropping students, but dropped all students off then what to do | Phase 1 | Bivash | [6 empty] | 18th Aug 2023 | Completed
4 | 10.004 |  | If schedule activity done by parent ,then how attendant knows it, student is absent or anything else. | Phase 1 | Bivash + Abir | [7 empty] | Completed | Done from Bivash's end, pending from Abir
5 | 10.005 |  | Exam Schedule Feature | Phase 1 | Neelabja |  |  |  | 5 days |  |  | 12.09.2023 | Completed | Will be deployed on 12.09.2023
6 | 10.006 |  | When ever in Admin > Schedule Activity is deleted, need to call below API In Pre-prod: http://111.93.179.197/SMSAPI/api/GatePass/DeleteActivity?activityID=11 In Prod: http://3.111.180.191/SMSAPI/api/GatePass/DeleteActivity?activityID=11 | Phase 1 | Neelabja | [7 empty] | Completed
7 | 10.007 |  | Need API to sync those Student & Guardian Added from SMS to Buzzed | Phase 1 | Neelabja | 1.New student add and map with guardian with one api. (checking needed if student and guardian is already exists) | [6 empty] | Completed | Done from Neelabja's end, pending from Arijit
8 | 10.008 |  | SMS Frontend to include new students availing Bus Services [Students needs to be added for Existing Guardian] | Phase 1 | Neelabja | [7 empty] | Completed
9 | 10.009 |  | Auto sink SMS & GPS system | Phase 1 |  | There will be one "SMS button " to push the data from sms to GPS 1. Table needs to be migrated 2. Auto sink SMS & GPS system | [6 empty] | Pending
10 | 10.01 |  | Socket implementation for live streaming GPS (On Node) for admin & mobile | Phase 1 | Shawon | [7 empty] | Completed
11 | 10.011 |  | Teacher Login - SMS Teacher to flow to GPS DB | Phase 1 | Shawon | Similar to Attendant, Guard user personas, for a Teacher User Type also need a login capability in School App | [6 empty] | Completed
12 | 10.012 |  | Socket Implementation Phase 1 | Phase 1 |  | A. Mapping of Route and Stoppage with following: 1. Define pickup and Dropoff time for each Route and Stoppage 2. Assign Driver and Attendant, Student, Teacher (Master Details) for each bus ⁠3. Once trip starts, system gets a track ID against the trip. Based on #Bus no and Route, socket is created.
|  |  |  | Phase 1 |  | B. 1.Once trip starts, system gets a track ID against the trip. Based on #Bus no and Route, socket is created. 2. After certain time (to be confirmed from Bivash) push the socket server log GPS Database 3. Socket server log to be saved on mobile side local DB on bulk basis till the trip ends and then pushed GPS Database.
|  |  |  | Phase 1 |  | C. Also, previously, on Parent App, Arrival on particular Stoppage, distance between bus and pickup/drop off stoppage was shown via API. Now here also, Socket will be implemented.
13 | 10.013 |  | GPS additional Suggestions | Phase 2 |  | https://riceindia-my.sharepoint.com/:x:/g/personal/alok1_ranjan_adamastech_in/EdX_zmo2uBRImPYna9SqmiMBDdgHEbkm1L23NuH6QHckhQ?wdOrigin=TEAMS-ELECTRON.p2p_ns.bim&wdExp=TEAMS-CONTROL&wdhostclicktime=1704710758593&web=1
Note on J2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 hours kept for bug fixes/other misc changes

## Ph 1, 2 generic
Backend Backlog - Generic
Sl No. | Story ID | Sprint No. | Feature | Phase | Resource | User Story | Task | Hours required | Delivery Date(Expected) | Delivered Date | Delivery Status | PMO Remarks | Backend Dev Remarks | Admin Changes | API changes | Mobile Dev Changes needed/Dependent
2 | 9.001 |  | If user is not registered yet and unable to login and need to show contact Admin > Show Admin Phone No | Phase 1 |  |  |  |  | TBD |  | Completed |  |  |  |  | Yes
3 | 9.002 |  | Session Timeout Popup Session expired. Please log in again. | Phase 1 |  |  |  |  | NA |  | Completed | Dependant on Bivash |  |  |  | Yes
4 | 9.003 |  | There is no option to sign up in this app. Then why login/sign up? Hence, Remove ''Sign up'' option | Phase 1 | [6 empty] | Completed |  |  |  |  | Yes
5 | 9.004 |  | Client wise or module wise we need to send flags as " Coming soon" or "Under maintenance " if a backend functioanlity is not available. Example - Fee Payment, Event & Calendar For Parent App | Phase 1 |  |  |  |  | TBD |  | Completed | Along with Lesson Plan |  |  |  | Yes
6 | 9.005 |  | Report generation for Term wise Teacher Performance Analysis. | Phase 1 |  | In an academic session, we have Term I & Term II for Classes I to IX , XI & Term I, Term II & Term III for Class X & XII. Under Term I & Term II there are different exams as mentioned in the excel sheet shared with you previously. In the existing report, we can generate report Teacher wise based on individual exam like AdcheckI, Adcheck II, Grade I. As per requirement of Ma'am Roy, the new report should be based on Total 100 marks after each term (Teacherwise). | Performance Analysis Report Teacher wise will be generated on Total 100 marks (including all modules for a term) after each term. |  | TBD |  | Completed |  |  |  |  | NA
7 | 9.006 |  |  | Phase 1 | [6 empty] | Completed | Dependant on Bivash |  |  |  | Yes
8 | 9.007 |  |  | Phase 1 |  |  |  |  | NA |  | Dropped | Not needed |  |  |  | Yes
| 9.018 |  |  | Phase 1 |  | Modify the existing procedures to support the following requirement: From Admin perspective, while fetching the records, Course and Term parameters shall be only mandatory, remaining all parameters (example - Subject, Class, Teacher etc.) shall be dynamic. |  |  |  |  | Completed |  | `
| 9.118 |  | Teacher Performance Analysis Report | Phase 1 |  | Teacher Performance Graphical Report 1. 2 options to show case as "Excel report" & " PDF report" 2. HTML View with graph, with result table. |  |  |  |  | In Progress
9 | 9.008 |  | Module wise data Migration from SMS to New DB tables | Phase 1 | [6 empty] | In Progress | Example - Mobile no correction from SMS to new DB table
12 | 9.011 |  | SMS Frontend to include new students availing Bus Services | Phase 1 | Arijit (P0) | 1. user shall be able to add students existing in school but new to bus services 2. Students Details (add/edit/delete) 3. Parents Details (add/edit/delete) | 1. Students needs to be added for Existing Guardian | 8 hours |  |  | Completed | Currently students are added via Buzzed Admin
13 | 9.012 |  | 1. Monthly Attendance Report 2. Attendance Analysis Report | Phase 2 |  | Late Coming MIS Report , Attendance Analysis Report (month wise) |  |  |  |  | Not Started
15 | 9.014 |  | Fee Collection, Pending Fee and Overall Status Reports | Phase 2 | [6 empty] | Not Started
14 | 9.013 |  | Dashboard & Hamburger Menu Optimization on Parent App | Phase 1 |  | 1. i. Upon landing on Dasboard > For Parent login > On top instead of showing 'Dashboard' show '<Student Name>' ii. Upon landing on Dasboard > For Teacher login > On top instead of showing 'Dashboard' show '<Teacher Name>' iii. Upon landing on Dasboard > For Attendant login > On top instead of showing 'Dashboard' show '<Attendant Name>' iv. Upon landing on Dasboard > For Security Guard login > On top instead of showing 'Dashboard' show '<Guard Name>' 2. On 'Account' > screen , show as 'App Version: 2.0.0 |  |  |  |  | Completed
15 | 9.014 |  | Dashboard & Hamburger Menu Optimization on Parent App | Phase 1 |  | 1. On Launch screen for Admin App, show the text as 'Welcome to the Management App', (include below line as 'Simplified school management ¦ Easy & Safe' 2. On Launch screen for Parent App, (include below line as 'Simplified school management ¦ Easy & Safe' before 'Welcome to the Parent App' |  |  |  |  | Dropped | As per design team's feeback
22 | 9.021 |  | DevOps | Phase 1 |  | Server Optimization (Weekly Basis) |  |  |  |  | Pending
23 | 9.022 |  |  |  |  | Database Backup (Weekly Basis) |  |  |  |  | Pending
24 | 9.023 |  |  |  |  | Error Log Maintenance and RCA email |  |  |  |  | Pending
16 | 9.015 |  | On Account changes (Parent App) | Phase 2 |  | 1. Account section to support below menu items in same sequence: i. Student Profile ii. Parent Profile iii. Gudian Profile iv. Settings v. My Documents vi. App Info - a. Contact Us b. Terms & Condition c. App version vii. About us a. School Info b. Contact Us Viii. Refer <App Name> |  |  |  |  | Pending
17 | 9.016 |  | On 'Account' screen, Student Profile > support below info inside the screen: (Parent App) | Phase 2 |  | 3. On 'Account' screen, Student Details > support below info inside the screen: i. Birthday ii. Gender iii. Blood Group iv. Roll No. v. Residential Address vi. Program (example - day borarding/day school etc.) |  |  |  |  | In Progress
| 9.017 |  | On 'Account' screen, Student Profile > support below info inside the screen: (Parent App) | Phase 2 |  | ** Change Profile Details icon/button to be supported under Student Details screen: On clicking this icon/button > Open the same form in editable form. upon submit, will display 'Your change request has been aceepted, it will be reflected once approved by admin'. | For approving the Edit, Support a backend menu item, to approve the changes in admin (similar to gatepass)
18 |  |  | On 'Account' screen, Student Profile > support below info inside the screen: (Parent App) | Phase 2 |  | Support 'Change Profile Details button'/Edit icon > Open Editable option for below info on the screen: i. Birthday ii. Gender iii. Blood Group iv. Residential Address Upon Submit, show following text as: 'Your change request has been acknowledged and will be applied after approval by the admin'.' |  |  |  |  | Pending
19 | 9.018 |  | Setting screen changes (Parent App) | Phase 2 |  | "Support following features under: Settings screen i. Notifications (toggle on/off) : text beneath (Receive instant updates on school events) a. Support (Requirements detailed in Task) Write to us: (Requirements for mail content detailed in Task) ii. Rate <App Name> - Navigate user to Play store/App store" | Mail Content: To: school admin mail id (example help@schooladmin.com Subject: Issue in Arivoo Parent <iOS/Andriod> App Body: Issue Details: User Details: User Name: John Doe Mobile No: 8933729201 School Name: <Auto filled> App version: <Auto filled> Current Time: <Auto filled> |  |  |  | Pending
20 | 9.019 |  | "On 'Account' screen, Teacher Profile > support below info inside the screen: (Teacher App) | Phase 1 |  | "On 'Account' screen, Teacher Profile > support below info inside the screen: Tab 1 (School info) 1. School Name 2. Academic Year 3. Staff Type 4. Department 5. Profile Picture Tab 2 ( Personal Info) 1. Name 2. Employee Id 3. Date of Birth 4. Gender 6. Joining Date 7. Contact No. & Email 8. Address" |  |  |  |  | Completed
21 | 9.02 |  | Library Management | Phase 2 |  | 1. Categorize Books 2. Issue Books 3. Search Books 4. Generate Bar Code 5. Return Books 6. Access from App 7. Alerts and Notifications 8. Membership Process Management 9. Subscription and Fines |  |  |  |  | Not Started
22 | 9.021 |  | Inventory Management | Phase 2 | [6 empty] | Not Started
25 | 9.02 |  | Client wise or module wise we need to send flags as " Coming soon" or "Under maintenance " if a backend functioanlity is not available. Example - Fee Payment, Event & Calendar For School App (Teacher Dashboard) | Phase 1 | [6 empty] | Pending |  |  |  |  | Yes
26 | 9.021 |  | Add validation at SP level for Due report to exclude/hide list of students taken TC, whenever report id fetched for AIS specifically. | Phase 1 |  | Historical Due Report excluding TC cases |  |  |  |  | Completed
29 | 9.024 |  | Bulk upload for Event & Calendar | Phase 2 | [6 empty] | Completed
30 | 9.025 |  | Connect Module | Phase 2 |  | Teacher can send out meessage to one individual student (in Parent App) via connect option 1. This feature shall be configurable (i.e communication shall be one way/two way) - If one way, only teacher can send the message in oneway where parent wont be able to reply but only view the message - If two way, both teacher and Parent can have conversation in the chat window |  |  |  |  | Not Started
31 | 9.026 |  | User Manual in general for SMS Admin and Mobile App | Phase 2 |  | Need to prepare user flow manual for all modules |  |  |  |  | In Progress
33 | 9.028 |  | Client Configuration | Phase 1 |  | Basic Client Configuration setup (Super Admin Vs Admin setup) 1. User Accounts and Roles: Create user accounts for the client's staff members and assign appropriate roles and permissions. 2. Customization: Configure the SMS application to match the client's specific needs, including branding (Brand creation, Brand Image, Mail/Phone, terminology, and custom fields. 3. Security Setup: Implement security measures, such as user authentication and data encryption 4. Support and Help Desk: Establish a support and help desk system for addressing client inquiries and issues promptly. |  |  |  |  | Not Started
34 | 9.029 |  | Client wise Multi Account Management for Client Fee Management | Phase 2 |  | Account level Settings |  |  |  |  | Not Started
35 | 9.03 |  | Brand Creation for Adamas Kids | Phase 1 |  | Adamas Kids to created as a separte brand within SMS |  |  |  |  | Not Started

## Events & Calendar
Backend Backlog - Events & Calendar
Sl No. | Story ID | Sprint No. | Feature | Phase | Resource | User Story | Task | Hours required | Delivery Date(Expected) | Delivered Date | Delivery Status | PMO Remarks | Backend Dev Remarks | Admin Changes | API changes | Dev Changes needed/Dependent
1 | 7.001 | Sprint 2 | New UI backend | Phase 1 | Parichoy | Academic calendar details entry to a new frontend page |  |  |  |  | Completed |  |  | Yes | Yes
2 | 7.002 | Sprint 2 | New UI backend | Phase 1 | Parichoy | Use specific Group Holiday Add Edit View | Validations for Holiday: For ADD: • Validation: Ensure all required fields are filled out when adding a holiday. • Error Message: "Please fill out all required fields to add a specific holiday." For EDIT: • Validation: Verify that the selected specific holiday exists before allowing edits. • Error Message: "The selected specific holiday does not exist or cannot be edited." AIS and AWS (Student specific, Day Boarding and Day School) • Validation: Confirm that the chosen academic calendar type (AIS, AWS, etc.) is valid. • Error Message: "Please select a valid academic calendar type." |  |  |  | Completed
3 | 7.003 | Sprint 2 | New UI backend | Phase 1 | Parichoy | Event Add, Edit, Delete listing View | This should driven by both Caldendar view & List view Validations for Event: For ADD: • Validation: Check if all required event details are provided during event creation. • Error Message: "Please provide all required event details to add an event." For EDIT: • Validation: Ensure that the event being edited exists and can be modified. • Error Message: "The selected event cannot be edited or does not exist." For Delete: • Validation: Verify that the event to be deleted exists and can be removed. • Error Message: "The selected event cannot be deleted or does not exist." Listing View: • Validation: Confirm that the list of events can be accessed. • Error Message: "Unable to retrieve the list of events." |  |  |  | Completed
4 | 7.004 | Sprint 2 | New UI backend | Phase 1 | Parichoy | In Create New Event, need to support capability of scheduling event for All user (with All + Multi Select option) only for the present Academic Year | 1. In user select All options, all underlying classes with All School Groups shall get selected (and disabled) 2. In Edit/View screen show those selected classes. Validations: If User Select "All" Options: • Validation: When "All" is selected, automatically select all underlying classes with All School Groups and disable further selections. • Error Message (if applicable): "You cannot select individual classes or school groups when 'All' is chosen." Edit/View Screen - Show Selected Classes: • Validation: Display the classes selected when creating the event on the Edit/View screen. • Error Message (if applicable): N/A (No error message is needed for this functionality). Events shall be shown for the current Academic year. User shall not be allowed to create Past/ Future Dated Events |  |  |  | Completed
5 | 7.005 |  |  | Phase 1 |  | Need to Add ''Announcement/Notice'' section in the backend Admin for following API: "/SMSAPI/api/Notification/GetDashboardAnnouncement" | In Mobile app we are showing Upcoming Events section (which needs to be renamed as Announement/Notice) once the backend Admin is enabled 1. Support differnt category as Annoucement/Notice. Base on configuration, which ever is applicable, system shall show this information in''Up coming events'' section . Also need to rename Upcomig events as Announcement / Notice) as and when applicable. Remaining time this shall be hidden. This Announcement /Notice should have categorization - As it can be Brand Specific, School Group spesific, Class & Section Specific and Individual student specifc (with ERP ID)rt 2. It should support Text Description, Publish Date & Time, image |  |  |  | Pending
6 | 7.006 |  |  | Phase 2 |  | Need to support Bulk Upload option for Event as per Event details. | Excel format shared in email |  |  |  | Pending
| 7.007 |  |  | Phase 1 |  | Event Planner Screen to be replaced as Academic Planner | Entire requirement has been shared in email as on 15.11.2023 Additionally, need a new screen (sub menu) Academic Planner Setup to mention classwise startdate and end date |  |  |  | Pending

## Result
Backend Backlog - Result
Sl No. | Story ID | Sprint No. | Feature | Phase | Resource | User Story | Task | Hours required | Daily hour allocation | Working Date Allocation | Delivery Date(Expected) | Delivered Date | Delivery Status | PMO Remarks | Additional Comments
1 | 8.001 |  | Result > Exam Result logic change for percentage |  | Sahidur/Arijit/Parichoy |  |  | 20 hours |  |  | 7th July |  | Completed
2 | 8.002 |  | Exam year classification (similar like transaction history), Download PDF options rule configuration Exam schedule Subject wise component for exam |  | Sahidur/Arijit/Parichoy | In case of different result publish pattern, Result template ID to be tagged with PDF. HTML Template to be created |  | TBD |  |  | 7th July |  | On Hold | On Hold
3 | 8.003 |  | Frontend setup for Result Calculations- 2screens Result Process and Display | [7 empty] | 12th July |  | On Hold | On Hold
4 | 8.004 |  | Live exam configuration data import in PP Server | Phase 1 | Sahidur |  |  | 8 hours | 6 hours | 11th July | NA |  | Completed
[9 empty] | 2 hours |  | 12th July |  | Completed
| 8.005 |  | All new table and field add in this DB |  | Sahidur |  |  | 4 hours | 4 hours |  | 17th July |  | Completed
| 8.006 |  | Partial Data migration (Class/Section/Parent and Student data Mapping etc) | Phase 1 | Sahidur |  |  | 8 hours | 4 hours | 18th July |  |  | Completed
[9 empty] | 4 hours |  | 19th July
| 8.007 |  | Result Data configure in New configuration system | Phase 1 | Sahidur |  |  | 8 hours | 4 hours | 20th July
[9 empty] | 4 hours |  | 21st July |  |  | To be done & tested during prod deployment
| 8.008 |  | All previous work setup in Production Server | Phase 1 | Sahidur |  |  | 8 hours | 4 hours | 24th July
[9 empty] | 4 hours |  | 25th July
| 8.009 |  | Subject codes needs to be updated (Frontend needed) |  | Sahidur |  |  | Part of #15 |  |  |  |  | Completed |  | Frontend will be still pending
5 | 8.0011 |  | Exam Exam Component Group Creation like(two addcheck merge) | Phase 1 | Susmita |  |  | 12 hours | 4 hours | 12th July | NA |  | Completed | Database part is still pending, need to generate template and PDF to show result | Will need some more changes to show complete result by Sept
[9 empty] | 6 hours | 13th July | NA
[9 empty] | 2 hours |  | 14th July
6 | 8.0012 |  | Result Listing and advanced searching - 12 hours | Phase 1 | Susmita |  |  | 12 hours | 6 hours | 17th July | NA |  | Completed | Advance Search is pending, Result Summary also needs to be added
[9 empty] | 6 hours |  | 18th July |  | Completed | Searching, Edit part is remaining to be done by 25th EOD
7 | 8.0013 |  | Exam Schedule Creation and listing, class & signature | Phase 1 | Susmita |  |  | 4 hours | 4 hours |  | 11th July | 14th July
8 | 8.0014 |  | Exam Schedule Grade Structure | Phase 1 | Arijit |  |  | 16 hours | 2 hours | 11th July | NA |  | Completed
[9 empty] | 6 hours | 12th July | NA
[9 empty] | 6 hours | 13th July | NA
[9 empty] | 2 hours |  | 14th July
9 | 8.0015 |  | Rules setup as per grade card rules | Phase 1 | Arijit |  |  | 12 hours | 6 hours | 17th July | NA |  | Completed | AIS is done, AWS need to be done (as per update received on requirement on 19/07 Blocker (Configuration pending from School's side). Will be done by them on 20.07.2023.
[9 empty] | 6 hours |  | 18th July
10 | 8.0016 |  | Report card showing for different 14 template for AWS (class/periodic assessment) - 32 hrs | Phase 1 | Susmita +Arijit |  |  | 32 hours | 6 hours + 6 hours | 19th July | NA
[9 empty] | 6 hours + 6 hours | 20th July | NA |  | Completed | 30% completed, Today EOD Target to complete (3 are completed out of 14 as on 21.07.23)
[9 empty] | 4 hours + 4 hours |  | 21st July
11 | 8.0017 |  | Report card showing for different template for AIS - NOT Provide Yet | Phase 1 | To be done along with AWS |  |  | To be done along with AWS |  |  |  |  | Completed | To be done along with AWS
12 | 8.0018 |  | Generate Report Card as PDF file | Phase 1 | Arijit |  |  | 4 | 4 hours |  | 24th July |  | Completed | 19th July EOD, dependant on #10
13 | 8.0019 |  | Result Publishing AWS | Phase 1 | Arijit |  |  | 1 | 1 hours |  |  |  | Completed
14 | 8.002 |  | Report Card show API for Buzzed | Phase 1 | Susmita |  |  | 4 hours | 4 hours |  | 24th July |  | Completed | Need to once discuss with Mobile team if new API needed or not
15 | 8.0021 |  | Provisional/Final Result Process | Phase 1 | Sahidur |  |  | 24 | 4 hours | 10th July | NA |  | Completed | Per discussion with Sahidur, Sl #15 has been postponed and to be performed after #4 all subt tasks are completed
[8 empty] | 24 hours | 4 hours | 11th July
[9 empty] | 4 hours | 12th July
[9 empty] | 4 hours | 13th July
[9 empty] | 4 hours | 14th July
[9 empty] | 4 hours |  | 17th July
16 | 8.0022 |  | Result Task process Front end screen | Phase 1 | Arijit |  |  |  | 4 hours | 25th July | 25th July |  | Completed
17 | 8.0023 |  | Report of Results for Students Marks | Phase 2 | [8 empty] | Not Started
18 | 8.0024 |  | Result AIS Data Migration | Phase 1 | Trideep | Only Class 10 and 12 as per result declaration to be done on 12th Aug | [6 empty] | Completed
19 | 8.0025 |  | Result AIS Data Migration | Phase 1 | Trideep | Remaining classes apart from 10 and 12 | [6 empty] | Completed
20 | 8.0026 |  | Result Process Rule Implementation as per AIS | Phase 1 | Arijit | [7 empty] | Completed
21 | 8.0027 |  | Result Process and Publishing | Phase 1 | Arijit (P0) | For Datebase, Backend and Mobile Changes | [6 empty] | Completed
22 | 8.0028 |  |  |  | Arijit (P0) | Subject Rules Setup | [6 empty] | Completed
23 | 8.0029 |  |  |  |  | Migration done, now frontend needed in Admin AIS and AWS | [6 empty] | Completed
24 | 8.003 |  | IGCSE Result Process | Phase 1 | Trideep | Cambridge IGCSE curriculum result process | [6 empty] | Pending | PMO needs to follow up for Result/Grade Structure for this Cambridge course
25 | 8.031 |  | AIS & AWS Term 1 Exam result | Phase 1 |  | Data Migration | [6 empty] | Completed
26 | 8.032 |  |  |  |  | Different Report Card Template Design | [6 empty] | Completed
27 | 8.033 |  |  |  |  | Report Card Data population | [6 empty] | Completed
Note on J2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 hours kept for bug fixes/other misc changes

## Routine, Homework
Backend Backlog - Routine (Teacher + Parent)
Sl No | Story ID | Sprint No. | Module | Feature | Phase | Resource | User Story | Task | Hours required | Daily hour allocation | Feature Available in SMS | Working Date Allocation | Delivery Date(Expected) | Delivered Date | Delivery Status | PMO Remarks | Additional Comments
1 | 16.001 |  | Routine (Teacher) | Class Routine Management System(weekly class schedule) | Phase 1 |  | Period Master |  | 2 hours | 2 hours |  |  |  |  | Completed | Please refer emails shared on Key components and Routine master
2 | 16.001 |  |  |  | Phase 1 |  | Student wise Subject allocation from SMS side | [7 empty] | Completed
3 | 16.002 |  |  |  | Phase 1 |  | Session, School Group, Day, Class and Section/Batch wise Period Mapping | Define Start Date and End Date | 4 hours | 2 hours |  |  |  |  | Completed
4 | 16.003 |  |  |  | Phase 1 |  | Selecting alternative teachers in replace of absentee teachers |  | 2 hours | 2 hours |  |  |  |  | Completed
5 | 16.004 |  |  |  | Phase 1 |  | Class/teacher wise class random generate routine |  | 24 hours | 8 hours |  |  |  |  | Completed
6 | 16.005 |  |  |  | Phase 1 |  | Additional class management(optional) | [7 empty] | Completed
7 | 16.006 |  |  |  | Phase 2 |  | Theory Vs Practical Class segregation | [7 empty] | Completed
8 | 16.008 |  |  |  | Phase 1 |  | Combined Classes Provision | [7 empty] | Completed
[5 empty] | Phase 2 |  | Extra Classes Provision for a day in a week
[5 empty] | Phase 1 |  | Disable option against any period in a week
9 | 16.009 |  | Routine (Parent) | Class Routine Management System(weekly class schedule) | Phase 1 |  | API for Student Routine Day and Period wise and also include Subject Name and Teacher | [7 empty] | Completed
10 | 16.01 |  | Routine (Admin Teacher) | Class Routine Management System(weekly class schedule) | Phase 1 |  | When Admin logs in, they should be able to check the Routine for All the Teachers. (whereas, when an individual teacher is logging in they should see Routine for themselves) | [7 empty] | Completed
11 | 16.011 |  | Routine (Parent) | Class Routine Management System(weekly class schedule) | Phase 1 |  | When Admin logs in, they should be able to check the Routine for All the Teachers. (whereas, when an individual teacher is logging in they should see Routine for themselves) | [7 empty] | Completed
12 | 16.012 |  | Routine All | Subject Allocation | Phase 1 | Susmita | 1. Allocation add | Validation: 1. Allocation Add: Error Message: "Please fill in all required fields to add the allocation." | 12 | [5 empty] | Done
13 | 16.013 |  |  |  |  | Susmita | 2. Allocation List | 1. Adv Search | 16 | [5 empty] | Done
14 | 16.014 |  |  |  |  | Susmita | 3. Allocation Edit | Validation: 1. Allocation Edit: Verify that the allocation being edited exists. Error Message: "The allocation you are trying to edit does not exist." | 4 | [5 empty] | Done
15 | 16.015 |  |  |  |  | Trideep | 4. Creation of sp related to subject allocation |  | 4 | [5 empty] | Done
16 | 16.016 |  |  | Class Roll Mapping | Phase 1 | Arijit | 1. List |  | 4 | [5 empty] | Done
17 | 16.017 |  |  |  |  | Arijit | 2. Class Roll number allocation | Validation: 1. Ensure that the selected roll number is available for allocation. Error Message: "The selected roll number is already allocated." | 12 | [5 empty] | Done
18 | 16.018 |  |  |  |  | Arijit | 3. Class Roll number allocation edit | Error Message: "The roll number allocation you are trying to edit does not exist." | 6 | [5 empty] | Done
19 | 16.019 |  |  |  |  | Trideep | 4. Creation of sp |  | 6 | [5 empty] | Done
20 | 16.02 |  |  | Routine | Phase 1 | Arijit | 1. Session and class wise total period assign | Validation: Ensure that the session and class combination is unique. Error Message: "A routine for the selected session and class already exists." | 8 | [5 empty] | Done
21 | 16.021 |  |  |  |  | Arijit | 2. Period and slot and week day mapping add | Validation: Ensure that the selected period, slot, and weekday are available. Error Message: "The selected period, slot, or weekday is not available for mapping." | 32 | [5 empty] | Done
22 | 16.022 |  |  |  |  | Arijit | 3. Period and slot and week day mapping edit | Validation: Verify that the mapping being edited exists. Error Message: "The mapping you are trying to edit does not exist." | 12 | [5 empty] | Done
23 | 16.023 |  |  |  |  | Arijit | 4. Period and slot and week day mapping listing |  | 8 | [5 empty] | Done
24 | 16.024 |  |  |  |  | Arijit | 5. Class routine generate add | Validation: Ensure that all required data for generating the class routine is provided. Error Message: "Please provide all required data to generate the class routine." | 16 | [5 empty] | Done
25 | 16.025 |  |  |  |  | Arijit | 6. Class routine edit | Validation: Verify that the class routine being edited exists. Error Message: "The class routine you are trying to edit does not exist." | 8 | [5 empty] | Completed
26 | 16.026 |  |  |  |  | SK Sahidur | 7. Sp creation |  | 12 | [5 empty] | Done
[7 empty] | Freeze functionality to be included for Routine | Before Submit button on Routine Generate screen, show below message: By checking this box you are agreeing to this one-time process for the ongoing academic year. Changes cannot be made without administrator approval. For any change requests, please contact the system administrator. In the backend, If Freeze active flag to be created based on selection on front end
27 | 16.027 |  |  |  | Phase 2 |  | Extra class | [7 empty] | Completed
28 | 16.028 |  |  |  | Phase 2 |  | Bulk routine upload | [7 empty] | Pending
29 | 16.029 |  |  |  | Phase 2 |  | Class Swapping | [7 empty] | Pending
30 | 16.03 |  | Homework (Teacher) | User assigns homework from 1. My Classes 2. Homework Module | Phase 1 |  | Navigation - 1. My Classes > Select Period > Homework > Assign New > Add Homework 2. Homework Module > Assign Homework | 1. Add Homework shall have options to select following: a. Class b. Subject c. Chapter d. Topic e. Subtopic f. Add Note and Attach Document | [6 empty] | Pending
31 | 16.031 |  |  | User can Edit/Delete Homework |  |  | Navigation - 1. Homework Module > Assigned Homework Tab > Open particular Homework > Edit/Delete | 1. Edit and Delete homework option shall be configurable Example - If Homework is assigned on 05/10/2023 , user can Edit / Delete it only on the assigned date. Next day it shall get moved to Due Homework Bucket and will be assigned to Parent App. | [6 empty] | Pending
| 16.032 |  |  | User checks homework from 1. My Classes 2. Homework Module |  |  | Navigation - 1a. My Classes > Select Period > Homework > Check >. Check Homework 1b. User can mark homework status for each student 2a. Homwork module > Due tab > specific Homework Card > Go to My classes (then same as My claases route) to check and mark | Display of Due Homework based on below logic: 1. First show by Due of Today's Date 2. Followed by Due Date in Ascending Order (Due from Previous Days First followed by Upcoming Date Once Teacher marks Homework as Completed, system shall record the log and show the time stamp and move it History | [6 empty] | Pending
| 16.033 |  |  | Homework History - check |  |  | Support 3 types of status: 1. Completed - User marked for all students 2. Partially Completed - User marked for only few students 3. Not Checked - User didnot mark for any student | Teaher can filter out based on (Default 1 month till today's date records) 1. Date 2. Class 3. Subject | [6 empty] | Pending
| 16.034 |  |  | Homework History - Update Homework Status |  |  | This is similar to Student Attendamnce Module | [7 empty] | Pending
35 | 16.035 |  | Homework (Parent) | Parent check homeworks |  |  | View Homework: cards shall be shown one by one (For each student): 1. First show by Due of Today's Date 2. Followed by Due Date in Ascending Order (Due from Previous Days First followed by Upcoming Date | Homework shall support below status : 1. Submitted (Already completed and marked by parents) 2. Due Tomorrow (Due date for homework submission is by tomorrow) 3. Upcoming due (Due date for homework submission is greater than tomorrow) 4. Pending (Due date for homework submission is already passed) | [6 empty] | Pending
[7 empty] | View Homework in detail: with Assigned Date, Due Date, Subject, Chapter, Topic/Subtopic, Assignment details Assignment attachment download | [7 empty] | Pending
36 | 16.036 | [5 empty] | View Homework: cards shall be shown one by one (For each student): 1. Filter by Due Date 2. Filter by Subject | [7 empty] | Pending
37 | 16.037
38 | 16.038
39 | 16.039
40 | 16.04
41 | 16.041
Note on K2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 hours kept for bug fixes/other misc changes

## Attendance, My Classes
Backend Backlog - Attendance, My Classes
Sl No. | Story ID | Sprint No. | Feature | Phase | Resource | User Story | Task | Hours required | Delivery Date(Expected) | Delivered Date | Delivery Status | PMO Remarks | Mobile Dev Remarks
1 | 14.001 |  | Student Attendance Class wise and Day wise attendance to be taken for each session (For Teacher persona) | Phase 1 |  | Day wise Attendance and Period-Subject Attendance Marking (Present Vs Absent) - On landing page, show list of periods already taken by the teacher for that day (data shall be driven from Routine) |  |  |  |  | Completed
2 | 14.002 |  |  |  |  | - Filteration option to see (Period wise, Date wise,Student Name wise) cards. |  |  |  |  | Completed
3 | 14.003 |  |  |  |  | In App > Student Attendance screen > the Check Attendance button for all the classes (cards) shall be enabled, for the user to mark attendance for the day based on time configurable from the backend. | i. For now the value to be set as Next Working Day 10 am. Post That the button shall be disabled. ii. On Next working day fresh list of classes shall appear to Edit the Attendance, once class has been taken from My Classes route already in the next day |  |  |  | Completed
4 | 14.004 |  |  |  |  | For Edit Class Attendance screen > If user modifies the attendance against class or any specific student, the updated changes should be stored in backend and reflect. |  |  |  |  | Completed
5 | 14.005 |  |  |  |  | . Add Log button shall be enabled, for the user to make entry based on time configurable from the backend.However, for now the value to be set as Next Working Day 10 am. i. Post next 10am, this button shall be disabled. |  |  |  |  | Completed
6 | 14.006 |  | My Classes (Teacher Persona) | Phase 1 |  | 1. On landing page, show list of periods to be taken by the teacher for that day (data shall be driven from Routine) |  |  |  |  | Completed
7 | 14.007 |  |  |  |  | 1. System shall support following three status types against each class card: a. Completed b. Ongoing c. Upcoming | Based on class status as completed, currently on going, upcoming, system shall update the status for each period within the mentioned time frame for each class (This shall be as per backend configuration) |  |  |  | Completed
8 | 14.008 |  |  |  |  | 1. Show on Daily basis (on Working weeks), based on Teacher's Routine the following, when user clicks on ''View More'' button against each card: a. Chapter b. Topic/Subtopic c. Objective d. Methodology e. Assignments |  |  |  |  | Completed
9 | 14.009 |  |  |  |  | From My classes support two actions: 1. Take Attendance 2. Fill up Log Book | On Attendance screen: For 1st period system shall only show the value for Total <count> of class. From the next classes onwards, system shall show values of all i.e. Total, Present and Absent on top panel, along with Toggle pre-selection (Present/Absent as selected in previous class). (Please refer PRD SR4.3 for more details) |  |  |  | Completed
10 | 14.01 |  | Attendance (For Parent Persona) | Phase 1 |  | Support Academic year wise Student Attendance record (for Pie chart) | This dashboard shall capture, Student's attendance status for the entire academic session: Show percentage for: i. Present ii. Absent |  |  |  | Completed
11 | 14.011 |  |  | Phase 1 |  | Capture Student's Class wise ((current year) + Previous year's class)) and Subject wise attendance | 1. For each class and Subject, system needs to show month wise Present/Absent count 2. Support Filter option to choose month wise option |  |  |  | Completed
12 | 14.012 |  |  | Phase 1 |  | Support showing graph for weekly and monthly attendance status for the student (for Bar Graph) |  |  |  |  | Completed
13 | 14.013 |  |  | Phase 1 |  | Support Schedule Leave feature | 1. In this feature , parent needs to create Leave Request 2. Once request requested, same shall be shown on Leave screen. 3. Support Leave History records for user to check in Leave History screen |  |  |  | Completed | This is to be taken up post delivery to AIS and AWS
14 | 14.014 |  |  | Phase 2 |  | Comprehensive & Comparative School Attendance Dashboard
15 | 14.014 |  | Attendance Entry | Phase 1 | Abhishek | 1. Teacher wise routine calender view |  | 24 |  |  | Completed
16 | 14.015 |  |  |  | Sayak | 2. Attendance entry |  | 6 |  |  | Completed
17 | 14.016 |  |  |  | Sayak | 3. Attendance view |  | 4 |  |  | Completed
18 | 14.017 |  |  |  | Sayak | 4. Attendance edit |  | 4 |  |  | Completed
19 | 14.018 |  |  |  | Trideep | 5. Sp creation |  | 12 |  |  | Completed
20 | 14.019 |  |  |  | Arijit | 6. API Creation {6 APIS} |  | 16
21 | 14.02
22 | 14.021
23 | 14.022
24 | 14.023
25 | 14.024 |  | Teacher's Attendance (Self) | Unavailability Phase 1 |  | Teacher Unavailability Listing screen: 1. Capture Teacher's unavailability request lists Date Reason Approval Status | Admin needs to approve/reject Unavailability request, similar to Gatepass Teacher Need backend Admin screen to Maintain the request logs, Approve / Reject request (similar to Gate Pass) Validations >Date: 1. Ensure the date field only accepts valid dates within an acceptable range. 2. Validate that past dates cannot be entered for unavailability requests. 3. Check that the date format is correct (e.g., MM/DD/YYYY or DD/MM/YYYY). >Reason: 1. Ensure the reason field is mandatory for every request. 2. Validate the length of the reason, ensuring it falls within acceptable limits. >Approval Status: 1.Ensure this field is initially set to "Pending" or a default status. 2.Admin should have the ability to change the approval status to "Approved" or "Rejected." 3.Implement proper validation to restrict any unauthorized changes to the approval status. Ensure the reason field is mandatory for every request. Validate the length of the reason, ensuring it falls within acceptable limits. |  |  |  | Completed
26 | 14.025 |  |  |  |  | 2. Teacher Replacement as part of Substitution for the absent teacher | 1. Routine module reflection (Parent + School app) 2. Attendance module reflection (Parent + School > Student Attendance) Validations: 1.Ensure that the information related to teacher replacements is updated in real-time or with minimal delay. 2.Validate that the replacement teacher's information (name, contact details) is correctly displayed. 3.Ensure that the parent and school apps reflect the same substitution data, avoiding inconsistencies. 4. Confirm that student attendance records are accurately updated to reflect the substitution. |  |  |  | Completed
27 | 14.026 |  |  |  |  | 3. Previously applied request logs (i.e. Request Approved/Rejected) to be shown (Similar to Fee Payment History) | Leave History Validations: 1. Validate the sorting and filtering options for request history, allowing users to find specific requests easily |  |  |  | Completed
28 | 14.027 |  |  |  |  | Teacher Unavailability Approval screen: Admin needs to approve/reject Unavailability request, similar to Gatepass Show below fields: 1. Teacher Name 2. Reason for unavailability 3. Date Range | Validations: 1.Teacher Name: Confirm that the teacher's name is displayed accurately, matching the request being reviewed. 2. Reason for unavailability: Ensure the reason for unavailability is clearly visible for the admin's review. 3. Date Range:Verify that the date range is accurately displayed. Ensure that the date range is consistent with the request being reviewed. |  |  |  | Completed
[6 empty] | Delete option for Pending Unavailability Request | Need to capture reason selected for Delete Validations: 1.Capture Reason Selected for Delete: a.Ensure that the admin must select a valid reason from the master reason list before deleting a request. b.Implement validation to prevent deletion without specifying a reason. |  |  |  | Completed
[6 empty] | Support Master reason list (for admin) to select Delete Reason | Validations: 1.Support Master Reason List (for admin) to Select Delete Reason: a.Verify that the master reason list is maintained and updated as needed. |  |  |  | Completed
29 | 14.028 |  |  | Attendance Phase 1 |  | Support Academic year wise Teacher Attendance record (for Pie Chart) - This data shall be based on Teacher's unavilabity marked: (i.e. when marked unavailable, for that date/time range, it will be considered as Absent. Remaining time it will be marked as Present. | This dashboard shall capture, teacher's attendance status for the entire academic session: Show percentage for: i. Present ii. Absent Validations: Verify that the attendance data covers the entire academic session and is not limited to specific date ranges. |  |  |  | Completed
30 | 14.029 |  |  |  |  | Capture teacher's Lecture wise count (This shall be as per Routine data) | 1. Show month wise count for following: a. Total Lectures Allocation: [Value] b. Lectures Scheduled till Date: [Value] c. Lectures Conducted till Date: [Value] d. Lectures Missed till Date: [Value] 2. Support Filter option to choose month wise option Validation: Ensure that the filter option allows users to select specific months for viewing lecture counts. |  |  |  | Completed
31 | 14.03 |  |  |  |  | Support showing graph for monthly attendance status for the teacher (for Bar Graph) |  |  |  |  | Completed
| 14.031 |  |  |  |  | 1. Within each month, Day wise support Status view for each period as 'Absent' and 'Present' 2. If status is not available for the day: a. Not yet updated b. No data |  |  |  |  | Completed
|  |  |  | Phase 2 |  | Teacher Attendance > Class wise selection view (both Admin and Teacher login type) and to see how many classes Attendance taken Vs How many to be updated yet per week (so that alerts can be sent) |  |  |  |  | Pending

## ERP, Lesson Plan, Log book
Backend Backlog - ERP, Lesson Plan, Logbook, Teacher Absence Management
Sl No. | Story ID | Sprint No. | Module | Feature | Phase | Resource | User Story | Task | Hours required | Daily hour allocation | Feature Available in SMS | Working Date Allocation | Delivery Date(Expected) | Delivered Date | Delivery Status | PMO Remarks | Additional Comments
1 | 11.001 |  | ERP | Class Master | Phase 1 | Parichoy | 1. Class Master 2. School Group (Day Boarding, Day School) 3. Mapping of School Group with Class Master 4. School group wise and class wise timing 5. Class, Section, Stream (for existing students) Mapping as per New Class ID and Section ID Master (including listing) | [7 empty] | Completed
2 | 11.002 |  |  | Session Master | Phase 1 | Parichoy | 1.Define Start and End Date for Acedemic Year/Session (varry school to school) |  |  |  | #1 needs to be implemented newly |  |  |  | Completed
3 | 11.003 | [5 empty] | 2. Define Course (Class) 3. Define Batch (Section) |  |  |  | #2 Single course creation is available #3 is available |  |  |  | Completed
4 | [6 empty] | 4. Mapping Batch with Course and Session 5. Map Course Family with session |  |  |  | Based on #1 implementation we need to map with #5 |  |  |  | Completed
5 | 11.004 | [5 empty] | 6. New implementation on bulk course structure creation a. Basic Course Creation (Before Admission) b. Bulk Course Structure Creation (NAMING CONVENTIONS NEEDS TO BE CHANGED) | [7 empty] | Completed
6 | 11.005 |  | Lesson Plan | Syllabus Master | Phase 1 | Sayak | 1. Subject Master creation | A. Subject Type to support: 1. Core (Mandatory) 2. Elective (Optional) B. Subject Listing | 20hours |  | No |  |  |  | Completed
7 | 11.005 |  |  | DB Table create/Business Flow/Data Flow analysis | Phase 1 | Sayak | Elective (Optional) Subject selection option during Admission | 1. While admission, by default along with mandatory subject, a radio button option for Elective (Optional) subject selection should be there 2. Once mapped, for each class, along with Mandatory, the Optional class should be shown. 3. As per selection of Student for the Elective classes, it will help with invoice and Subject result marking |  |  | No |  |  |  | Pending
9 | 11.006 |  |  |  | Phase 1 | Abhishek | Teacher Master Creation | Teacher Profile Information (Basic Details, Address, Qualification etc. Note: For now only minimum info needed for creation | 20hours | [5 empty] | Completed
10 | 11.007 |  |  |  | Phase 1 | Abhishek | Teacher tagging with Class + Subject wise component (primary and secondary class wise) |  | 8 hours | [5 empty] | Completed
| 11.008 |  |  |  | Phase 1 |  | 3. Lesson Objective | [7 empty] | Completed
[5 empty] | Phase 1 |  | 4. Methodologies | [7 empty] | Completed
[5 empty] | Phase 2 |  | 5. Procedures or Steps | [7 empty] | Completed
[5 empty] | Phase 2 |  | 6. Discussion and Review section | [7 empty] | Completed
[5 empty] | Phase 2 |  | 7. Assessment section | [7 empty] | Completed
[5 empty] | Phase 2 |  | 8. Enrichment section is for students' activity. Need to plan some activity or homework which can help the students to practice on their own and make their understanding profound of the lesson/topic learned. | [7 empty] | Pending
[5 empty] | Phase 2 |  | 9. Define Assignments for Students | [7 empty] | Completed
| 11.009 |  |  | Admin | Phase 1 | Susmita | Methodology Category Subject and Session wise Add |  | 24 hours | [5 empty] | Completed
| 11.01 |  |  |  | Phase 1 | Susmita | Methodology Category List | [7 empty] | Completed
| 11.011 |  |  |  | Phase 1 | Susmita | Methodology Category Edit | [7 empty] | Completed
| 11.012 |  |  |  | Phase 2 | Susmita | Methodology Category wise Activity Create with Measure Unit (Text/Percentage/Multi Choice/Single Choice/ Time/Assignment) and Flagged (at the time of comes in topic add) | [7 empty] | Completed
| 11.013 |  |  |  | Phase 2 | Susmita | Methodology Activity List | [7 empty] | Completed
| 11.014 |  |  |  | Phase 2 | Susmita | Methodology Activity Edit | [7 empty] | Completed
| 11.015 |  |  |  | Phase 1 | Parichoy | Subject Template Create(Chapter/Topic) as per brand ID |  | 48 hours | [5 empty] | Completed
| 11.016 |  |  |  | Phase 1 | Parichoy | Subject Template List | [7 empty] | Completed
| 11.017 |  |  |  | Phase 1 | Parichoy | Subject Template Edit | [7 empty] | Completed
| 11.018 |  |  |  | Phase 1 | Parichoy | Template Wise Subject Structure(Chapter/Topic Value) Create - Methodology wise data upload(like assignment) | [7 empty] | Completed
| 11.019 |  |  |  | Phase 1 | Parichoy | Template Wise Subject Structure List | [7 empty] | Completed
| 11.02 |  |  |  | Phase 1 | Parichoy | Template Wise Subject Structure Edit | [7 empty] | Completed
| 11.021 |  |  |  | Phase 1 | Parichoy | Day wise Chapter Topic Map | [7 empty] | Completed
4 | 11.022 |  | Lesson Plan Part (including Log Book) | Class wise and Day wise Log book to be filled up for each session | Phase 1 |  | 1. Class/Subject wise Teacher Entry for Logbook on day to day basis - On landing page, show list of periods already taken by the teacher for that day (data shall be driven from Routine) - Filteration option to see (subject wise, class wise, Day Boarding/Day School etc. grouping wise) cards. |  | 16 hours | [5 empty] | Pending
| 11.023 | [5 empty] | 3. For Add Log screen (capture, everything entered fresh) 4. For Edit Log screen (system needs to prepopulate the previously entered data. However, if users updates any information, need to save the changes) | a. Add Log button shall be enabled, for the user to make entry based on time configurable from the backend.However, for now the value to be set as Next Working Day 10 am. i. Post next 10am, this button shall be disabled. ii. On Next working day fresh list of classes shall appear to Edit/Add Log Book, once class has been taken from My Classes route already in the next day. b. System shall display Chapter, Topic, Subtopic name (in both Add Log and Edit Log Screen as entered as part of Lesson Plan | [6 empty] | Pending
| 11.024 | [5 empty] | Day to Day Completion percantage capturing and Status value Capturing for: 1. Not Started 2. Completed 3. Partially Completed a. In case of Partially Completed Status, need to capture the Percentage entered by Teacher | In case of Partially Completed task, the percentage needs to be stored. This should help with Teacher's evaluation report to be generated monthly in Phase | [6 empty] | Pending
| 11.025 | [5 empty] | Remarks Capturing as per teacher's entry | [7 empty] | Pending
| 11.026 | [5 empty] | Assignnments to display (as per submitted in Lesson Plan). However, need to capture the (toggle on/off) response (i.e. whether assignment has been alloted to class or not) | [7 empty] | Pending
| 11.027 |  |  | Admin |  |  | Logbook Entry Topic wise - All methodology wise data capture |  | 25 hours | [5 empty] | Completed
| 11.028 | [5 empty] | Subject and Topic wise all capture data Show in List | [7 empty] | Completed
[7 empty] | LogBook Feedback by Farooque Da (on 13.12.2023): 1. Once Search Parameter is selected, show the Day 1 card should be open and search box should get collapsed. 2. Day wise two buckets/section shall be shown as 'Assigned' and 'Unassigned'. 3. Search option be to be shown on the Day Header 4. <Month> - Day < > - Current Month to be added before Day in the header 5. Green color to be changed as per theme (globally) days (Monday, Tuesday, Wednesday..) etc font size to be shortened. (globally) 6. Search box to be more sleek (globally) 7. Few more error messages to be replaced (already provided) 8. Search box functionality for days in floating mode. Based on search user can open abd check see that day in open | [7 empty] | Pending
Note on K2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 hours kept for bug fixes/other misc changes

## Reports, Adm, Exam, Fee, Stu In
SMS Backend (Admin) Backlog
Sl No. | Story ID | Sprint No. | Module | Feature | Phase | Resource | User Story | Task | Hours required | Delivery Date(Expected) | Delivered Date | Delivery Status | PMO Remarks | Mobile Dev Remarks
5 | 12.005 |  | SMS Admin | Multi Branches under one Admin | Phase 2 |  | Multiple Brand ID/School Branches connect under same Admin so that Admin can switch and check branches under same login |  |  |  |  | Pending
6 | 12.006 |  | SMS Admin | Teacher Attendance Report | Phase 2 |  | Parameters to consider for Report: 1. Working Days 2. Attendance Mode 3. Attendance Threshold 4. Period Wise Attendance Tracking as per Routine 5. Substitution/Proxy | Automatic Attendance (if there, need to consider RFID based Time Tracking and Time Capture Multiple devices configured on a platform for a school or a branch and all of them synced with each other in real time. |  |  |  | Pending
7 | 12.007 |  | SMS Admin |  | Phase 2 |  | 1. Bulk Attendance Upload Feature (from previous attendance record during migration) Teacher |  |  |  |  | Pending
8 | 12.008 |  | SMS Admin |  | Phase 2 |  | Teacher Attendance Regularization |  |  |  |  | Pending
10 | 12.01 |  | SMS Admin | Admin (role) to be created, where Reception person can create Gatepass on behalf of Parent and Admin (School) can approve the gatepass | Phase 2 |  | Scenario : There is a parent who doesn’t have a smart phone and want to take his/her ward early using gate pass. Parent will contact school reception. Receptionist will initiate the same from Admin portal on behalf of parent, Admin will approve the same and while leaving the campus Security will scan the QR Code from ID card and close this.
12 | 12.012 |  | SMS Admin | Report of homework submission by students. | Phase 2 | [6 empty] | Not Started
11 | 12.013 |  | Reports | Adcheck Analysis Report for Teacher AIS | Phase 1 | [6 empty] | Dropped | Old SRSS report have been deployed
12 | 12.014 |  | Reports | Marks Tabulation Report for Teahcer AIS | Phase 1 | [6 empty] | Dropped | Old SRSS report have been deployed
15 | 12.017 |  | Exam Management Module > (Super Admin, Admin and Teacher Login) | Exam Schedule View, List | Phase 1 |  | 1. Configuration to be added for (example - Marks Vs Grade Total Marks Vs otal Grade) 2. Exam Name, Exam Date Range. Exam Publsih Date, Class / Stream wise
16 | 12.018 |  |  | Exam Schedule Details Add/Edit | Phase 1 |  | Paper wise date entry - Exam Routine Details - Class wise - Subject wise - Exam wise
17 | 12.019 |  |  | Exam Configuration | Phase 1 |  | Configuration setup: 1. Previous exam Marks to be considered within the current academic year (which all to be taken) 2. Or only Current exam Marks to be considered 3. Based on Previous exam(s) + Current exam, weightage to be determined
18 | 12.02 |  |  |  | Phase 1 |  | 1. Exam Component Master to be configured like- Ad Check Grade 1 Grade 2 Internal Viva Term
19 | 12.021 |  |  | Class wise exam grade master with category |  |  | Result wise gradation (scholistic vs co-scholistic)
20 | 12.022 |  |  | Admit Card Download sreen | Phase 1 |  | Exam Routine view (Printable) based on Exam Schedule, Class wise, Date wise, Subject wise
21 | 12.023 |  |  | Exam Marks entry screen | Phase 1 |  | Exam Attendance entry and Marks entry page Class, Student and subject wise
22 | 12.024 |  |  | Result Process and Report card generaion | Phase 1
23 | 12.025 |  |  | Tabulation sheet | Phase 1 |  | Tabulation sheet (report) - Printable to be generated Exam schedule wise (Class, Subject, Date )
24 | 12.026 |  |  | Exam Management Foil (Not Must but good to have feaure) | Phase 2 |  | Attendance sheet (Printable, Fillable) to be created for Harcdopy signature based on Exam Date Student Name Roll No Subject Class
25 | 12.027 |  |  | Marks entry Alteration with permission and log | Phase 2 |  | Once result is processed, To correct marks/update marks, support a new window to update the marks, once updated, same will be updated in Marks Entry page Individual student wise, Result Process and Report card generate option
26 | 12.028 |  |  | Landing Dashboard graphical representation | Phase 1 if time permits. Else, phase 2 |  | 1.Total no of Students Vs present today 2.Total no Teaching staff Vs present today 3.Year wise Total Pre enquiry applications vs Admission conversion graph 4. Year wise Total Payment collection so far vs remaining payment
Exam Subject sequence shown for gradecard needs to be supported on SMS Frontend
27 | 12.029 |  | Pre-Enquiry/Pre-Admission Management > Admin | 1. Pre-enquiry creation 2. Create Enquiry 3. Edit Enquiry 4. List and View | Phase 1 |  | 1. Pre- enquiry info to be same as SMS Pre-Enquiry screen 2. Create Enquiry Info same as Admission Management (#12.033) Note: Ref Enquiry No is created at this stage |  |  |  |  | Completed
28 | 12.03 |  |  | Prospectus creation and Payments screen | Phase 1 |  | In order to generate a prospectus, user needs to create Ad hoc receipt. |  |  |  |  | In Progress
29 | 12.031 |  |  | Follow-up screen | Phase 1 |  | Follow up creation (Followup done or not to be recorded) Response status: Log to be generated, |  |  |  |  | Completed
30 | 12.032 |  |  | 4 | Phase 1 |  | API integration needed between online/ Lead management and SMS backend
31 | 12.033 |  | Admission Management | Student Admission: Student Information screen - Add/ Edit, View, Listing Listing and View Section 1: Search by School Group, Class, Section, Name Section 2: Datagrid: Fields to support: Student Name, Class, Section, Student Id, Father Name, Action | Phase 1 |  | 1. Student Information - Add//Edit First Name Middle Name Last Name Birth Date (dd/mm/yyyy) Age Gender Blood Group Nationality Student Photo (upload) (jpg,jpeg,gif,bmp format) School Program Type (Day Boarding/Day School) Student Clubs & Houses Class Applied for - 2. Previous Academic Record School Name, School Adress, Marks obatinted in last class (%) |  |  |  |  | Completed
[7 empty] | 2. Communication Information: a.Residential Address (Address, Country,State, City Pincode) b. Permanent Address (Address, Country,State, City Pincode), Same as Residential Address checkbox c. Mobile No., Email Id |  |  |  |  | Completed
[7 empty] | 3. Student Qualification and Identification Documents Documents to be uploaded and shown (Basic and Educational, Achievement) a. Degree & Certificates > - Institute Name, Board, From Year - To Year, Add Attachment option b. Identity Documents > Aadhar/Pan/Birth certificate - Document Id Number, Full Name, Father's Name, Date of Birth, Issued on, Add Attachment option |  |  |  |  | In Progress
[7 empty] | 4. Transport Details - (only declaration status and Fee amount) |  |  |  |  | Pending
[7 empty] | 5. Hostel Details - (only declaration status and Fee amount) |  |  |  |  | Pending
[7 empty] | 6. Fee Payment Details (same as Old SMS) |  |  |  |  | In Progress
[7 empty] | 7. Student ID Card Generation process) |  |  |  |  | Pending
[5 empty] | Phase 2 |  | 4. Interview Assessment Test Details (Cumulative Marks) 5. Entance exam eligibility details 6. Recommendations and Statement of Purpose 7. Merit Based Scholarship
[5 empty] | Phase 1 |  | 8. Sibling Information Sibling student name, Student Id |  |  |  |  | Completed
|  |  |  | Admin level Approval work flow for availing discount, should be Role Based. | Phase 2 | [6 empty] | Pending
32 | 12.034 |  |  | Admission Criteria | Phase 1 |  | Differnet parameters to support: 1. Student Age 2. Previous Academic Record (Marks obained) 3. Family income, 4. Sibling (if any) - Details, concession 5. Employee Parent Details |  |  |  |  | Completed
26 | 12.035 |  |  | Mapping of Subject Structure Rule setup Session and Class wise | Phase 1 |  | - This is to be redirected for Routine and Subject Allocation for students Subject (Elective/Optional Selction) |  |  |  |  | Pending
27 | 12.03 |  |  | Student will be able check Subject information from mobile app for each academic year | Phase 2
28 | 12.031 |  | Admission Management > Student Login | Student needs to enter ERP id and Registered mobile no: | Phase 2 |  | User can check all the below details/screen wise features similar to mobile app: 1. Result 2. Fee 3. Attendance 4. Routine 5. Event & Calendar 6. Gatepass 7. Homework 8. Course plan
| 12.036 |  | Student Information Management | Student Information - List, View, Edit | Phase 1 |  | BRD shared |  |  |  |  | In Progress
|  |  |  | Student Promotion Screen | Phase 1 |  | 1. For each academic year, Student Listing to be shown (class and section wise) for next academic year batch/class movement - Promotion From Batch - Promotion To Batch Remarks column to be supported for each row. - in case not promoted remarks reason to be filled. - Approve Student Promotion Button - Bulk Approve promotion - Fee status check option against students |  |  |  |  | Pending
|  |  |  | Student Transfer | Phase 1 |  | Student leaving school as part of Transfer to be inititaed and approved |  |  |  |  | In Progress
|  |  |  | Stream and section change Provision | Phase 1 | [6 empty] | Pending
|  |  |  | Student ID Card generation | [7 empty] | Pending
|  |  |  | Student Admit Card Generation |  |  | Each Academic Year, Admit Card to be generated and shared based on configurable considerations on Fee / Attendance Status |  |  |  |  | Pending
|  |  |  | Reactivation of students in backend for Re admission purpose (where student has taken TC previously) | Phase 1 |  | New Ref id to be generated. And Previous data from old entry to be fetched against new ref id. |  |  |  |  | Pending
|  |  | Fee Management | Fee (Type) Category Master (Example Admission, Re-Admission, Ad-hoc) | Phase 1 | [6 empty] | Completed
|  |  |  | Fee Component Master (Example differnet fee type Transport, Library etc.) - Add, Edit, Listing | Phase 1 | [6 empty] | Completed
|  |  |  | Fee Structure - Add, Edit, Listing | Phase 1 |  | Select Catagory (for each academic year class wise and school group wise) 1. Lumpsum, Installement 2. Each Classes (Including differnent school groups) can have multiple fee plan (considering discount, scholarship amount etc) |  |  |  |  | Completed
|  |  |  | Fee Structure Year to Year Fee Structure Copy Feature Screen | Phase 2 |  | Copy /Clone feature for different class wise to use Common Fee Structure |  |  |  |  | On Hold
|  |  |  | Fee Structure List |  |  | Map fee schedule with academic session |  |  |  |  | In Progress
|  |  |  | Fee Structure (Student specific) Preview | Phase 1 |  | Invoice generation |  |  |  |  | In Progress
|  |  |  | Student Payment Invoice generation details screen | Phase 1 |  | Transaction (Offline/Online) Payment Details for each student wise |  |  |  |  | Pending
|  |  |  | Integration with Finance (Client wise) | Phase 1 |  | Temp table voucher to be insterted |  |  |  |  | Pending
|  |  |  | Student lead vs Student Followed up Vs Succesful conversion | Phase 2 |  | Fee Component
|  |  |  | Fine Master Setup | Phase 1 |  | Attributes: Fine Calculation Type as (Percent/Fixed) Time Period as Monthly or Day wise Grace period Range and Amount (Add Func) |  |  |  |  | Pending
|  |  |  | Adhoc Payment Receivable | Phase 1 |  | Admission Compulsion Flag to be added Ad hoc Fee Bulk Upload Option Ad Hoc Add and List screen |  |  |  |  | Pending
|  |  |  | Payment Receivable | Phase 1 |  | Student specific Current, Previous and Future Dues to be displayed and available for Payment |  |  |  |  | Pending
|  |  |  | Collection Register | Phase 1 | [6 empty] | Pending
|  |  |  | Payment Settlement | Phase 1 | [6 empty] | Pending
|  |  |  | Transport Fee Master Setup | Phase 1 | [6 empty] | Pending
|  |  |  | Hostel Fee Master Setup | Phase 1 | [6 empty] | Pending
|  |  |  | Student Promotion | Phase 1 |  | Yearly Promotion and Re-admission |  |  |  |  | Pending
|  |  |  | Payment Dashboard | Phase 1 |  | Payment Dashboard to be centralized for Prospectus Payment, Admission Payment and Ongoing Academic Payment - List - Individual Payment page - Receipts and Invoice generation |  |  |  |  | In Progress
|  |  |  | Freeze functionality to be included for Fee Structure | Phase 1 |  | Before Submit button on Fee Structure screen, show below message: By checking this box you are agreeing to this one-time process for the ongoing academic year. Changes cannot be made without administrator approval. For any change requests, please contact the system administrator. In the backend, If Freeze active flag to be created based on selection on front end |  |  |  |  | Pending
[5 empty] | Phase 2 |  | Discount, Special Fee, Scholarship - Amount to be adjusted against Fee Head

## User Role, Transport, Hostel
Backend Backlog - User Role Management
Sl No. | Story ID | Sprint No. | Feature | Phase | Resource | User Story | Task | Available in Current SMS | Hours required | Delivery Date(Expected) | Delivered Date | Delivery Status | PMO Remarks | Mobile Dev Remarks
1 | 15.001 |  | User Management: | Phase 1 | Abhishek | a. Create User b. Edit User c. Delete User (Soft Delete i.e Active/Inactive) Advance Search | User Creation > Validation: Verify that all required user details are provided. Error Message: "Please provide all required user details for user creation." User Edit > Validation: Verify that the user being edited exists. Error Message: "The user you are trying to edit does not exist." User Deletion > Validation: Verify that the user being deleted exists and is not associated with any critical data. Error Message: i. "The user you are trying to delete does not exist." ii. "Cannot delete this user as they are associated with critical data." | Delete is not there |  |  |  | Completed
2 | 15.002 |  | Role Management 1. Define Roles | Phase 1 | Sayak | Role Type (example - Admin, Super Admin, teacher) Role Name (example - Finance, Exam Department, Admission) Add Edit Listing | Validations: Ensure that the Role Type + Role Name (mentioned) is unique. Error Message: 1. "Role type already exists. Please choose a different role type'' 2. ''Role name already exists. Please choose a different role name." | Yes |  |  |  | Completed
3 | 15.003 |  | Permission Management | Phase 1 | Sayak | Add Edit Listing | Combine Roles with Permission |  |  |  |  | In Progress
4 | 15.004 |  | Assigning Roles to the user | Phase 1 | Sayak | This will map, User with the Roles and once they login, user shall be able to work on only those specific roles (where Roles are already entitled to each module #2) | Combine User with Roles Role Assignment to User > Validation: Ensure that the assigned roles are valid roles that exist in the system. Error Message: "One or more assigned roles are invalid. Please choose valid roles." | Yes |  |  |  | In Progress
5 | 15.005 |  | Assigning User with Branch/Brand + School Group and Class | Phase 1 | Abhishek | Example Mapping users with AIS and AWS | User Assignment to Branch/Brand > Validation: Ensure that the selected branch/brand is valid. Error Message: "The selected branch/brand is invalid. Please choose a valid branch/brand." | Yes |  |  |  | In Progress
6 | 15.006 |  | Permission Mapping with Roles | Phase 1 | Sayak | The users/role which are created to be mapped with Modules/Features like Academic, Finance. And, the subset/subfeatures to be auto mapped with the Role | Validation: Ensure that the selected modules/features are valid. Error Message: "One or more selected modules are invalid. Please choose valid modules." | No |  |  |  | In Progress
7 | 15.007 |  | Audit Trail Management/ Log Management | Phase 2 | [7 empty] | Pending
8 | 15.008 |  | 6. Duplication / Cloning of User and Assignment of Role | NA |  |  | User Duplication > Validation: Ensure that the duplicated user's details are unique, including username or email. Error Message: "A user with the same username or email already exists. Please choose a different username or email." Verify that the role being assigned exists. Error Message: "The role you are trying to assign does not exist." | No |  |  |  | Dropped | Per suggestion of Sahidur this is dropped
9 | 15.009 |  | Menu Master for within Permission and Menu Management | Phase 1 | Sayak | Create Menu , Sub menu Assign menu with Permission (Page Activity Master) Assign with Role (User Role Mapping) - Assign Brand, School Group, Batch, Class, Section , Stream | [5 empty] | In Progress
10 | 15.01 |  | Permssion wise access for User in Admin Panel | Phase 1 | Swadesh | [6 empty] | In Progress
11 | 15.011 |  | Transport Management
13 | 15.012 |  | Hostel Management

## Mobile Dev
Mobile Dev Backlog
Sl No. | Story ID | Sprint No. | Module | Feature | Phase | User Story | Hours required | Delivery Date(Expected) | Delivered Date | Delivery Status | PMO Remarks | Resource | Mobile Dev Remarks
1 | 13.001 |  | Event & Calendar | New UI /UX for Frontend based on Design team suggestion | Phase 1 |  |  |  |  | Completed |  | ABIR / TAMMIM
2 | 13.002 |  | Generic | If user is not registered yet and unable to login and need to show contact Admin > Show Admin Phone No | Phase 1 |  |  |  |  | Completed |  | ABIR
3 | 13.003 |  | Notification | Notification Setting | Phase 2 |  |  |  |  | Not Started
4 | 13.004 |  | Generic | Shimmer effect across platform for all modules | Phase 2 |  |  |  |  | Not Started |  | Ankit
5 | 13.005 |  | Generic | Ipad screens for Parent App | Phase 2 |  |  |  |  | Not Started |  | Ankit
6 | 13.006 |  | Student Attendance | Attendance UI/UX | Phase 1 | Teacher Marking Student's Attendance |  |  |  | Completed
7 | 13.007 |  | Student Attendance | Attendance Dev | Phase 1 |  |  |  |  | Completed
8 | 0.014 |  | Fee Payment | On Transaction Histroy > Fee Payment Receipt for 2nd time download, system shall show Duplicate Record with Watermark | Phase 1 |  |  |  |  | Oh Hold | This is API dependent and marked under story id #0.014 on Fee Payment Module
9 | 13.008 |  | Fee Payment | On Transaction Histroy > Fee Payment Receipt, if No Payment Receipt is available, upon clicking system shall not show blank page, instead provide message ''Please contact Admin'' | Phase 1 |  |  |  |  | Pending
10 | 13.009 |  | Gatepass | 1. User can't create gatepass during Holiday & gate pass can be create only working week 2. Insteed of multiple child now user can create gate pass only for single child only at a time. | Phase 1 |  |  |  |  | Completed |  | ABIR
11 | 9.017 |  | Generic | Regional Language support for Local schools | TBD | Across Admin and Parent App |  |  |  | TBD | This is API dependent
12 | 9.018 |  | Generic | Banner Dashboard | TBD | This will be used for school marketing |  |  |  | TBD | This is API dependent
13 | 9.019 |  | Generic | Write to school | TBD | To connect with school directly |  |  |  | TBD | This is API dependent
13 | 13.009 |  | Generic | Note book to save personal notes on APK | TBD |  |  |  |  | TBD
14 | 9.02 |  | Hamburger Menu | 1. My Profile (Add, Edit, Delete Profile Photo, Address) 2. Student Attendance QR Code 3. My Docs/Certificate section 4. FAQs 5. Language Change Option 6. Theme Change 7. About Us (School) 8. Gallery 9. About App, Referal Link | TBD |  |  |  |  | TBD | This is API dependent
12 | 13.011 |  | Schedule Activity | 1. User can't create activity during Holiday & gate pass can be create only working week 2. Insteed of multiple child now user can create activity only for single child only at a time. | Phase 1 |  |  |  |  | Completed |  | ABIR
13 | 13.012 |  | Event & Calendar | Event & Calendar (API Dependancy) for changes related to AIS | Phase 1 | School Group + Stydent ID both needs to added in API as parameters |  |  |  | Completed
14 | 13.013 |  | Fee Payment | Remove Additioal step to show student details in Parent App > Fee Payment module | Phase 1 |  |  |  |  | Completed |  | ABIR
15 | 13.014 |  | Generic | User Manual in general for SMS Admin and Mobile App | Phase 2 |  |  |  |  | Not Started
16 | 13.015 |  | Bus Tracking | Uber is showing the Timing minor Details on the lock screen itself. we can design like this for bus tracking. for phase2. | Phase 2 |  |  |  |  | Not Started |  | Ankit
17 | 13.016 |  | My Attendance | Academic year dropdown upon landing page only instead of inside page (similar for Student Attendance dashboard also) | Phase 2 |  |  |  |  | Not Started |  | Ankit
18 | 13.017 |  | Student Attendance | Schedule leave Attdendance | Phase 2 |  |  |  |  | Not Started |  | Ankit
19 | 13.018 |  | My Classes | Upcoming class section to be supported | Phase 2 |  |  |  |  | Not Started |  | Ankit
20 | 13.019 |  | Homework | Parent and School App should support Remarks for Individual student | Phase 2 |  |  |  |  | Not Started |  | Ankit
21 | 12.029 |  | Exam Mgt | Student will be able check Subject information from mobile app for each academic year | Phase 2 |  |  |  |  | Not Started |  | Ankit
Fee Head, Structure, Fee Component , class wise academic structure for fee component, student wise invoice & Payment

## Enhancements
Phase 2 Enhancements
Sl No. | Story ID | Sprint No. | Module | Feature | Phase | User Story | Hours required | Delivery Date(Expected) | Delivered Date | Delivery Status | PMO Remarks | Resource | Mobile Dev Remarks
1 |  |  | Reports | Historical Due report (Report loading time optimization)