## REPORTS_BUGLIST
# Id | QA Round | Module | Bug Type | Bug Description | BUG Status | Dev Assign | Priority | Severity
ID_001 | Round 1 | Examination State Report | Functional | By default should not select any exam state and exam list | Open |  | P2
ID_002 | Round 1 | Examination State Report | UI | Download icon should be there for all status button | Close
ID_003 | Round 1 | Examination State Report | UI | Report tittle name should be changed in the Report List | Open |  | P1
ID_006 | Round 1 | Student Attendance report | Functional | By selecting a custom range for future date its infinity loading | Close
ID_007 | Round 1 | Student Attendance report | Functional | No reports is getting generated for the recent classes though in admin its reflecting in online attendance logs | Close
ID_008 | Round 1 | Student Attendance report | Functional | For previous classes also no reports are getting generated | Close
ID_009 | Round 1 | Student Attendance report | Functional | If all 4 fields are mandatory to give then search buttin should be disabled | Close
ID_010 | Round 1 | Student Attendance report | Functional | If no data is thier the graph should not display | Close
| Round 2 | Student Attendance report | UI | Ui for datee is breaking | Close
| Round 2 | Student Attendance report | Functional | If user has searched for a attendance having no data >> after changing its displaying no rec but data is getting downloaded | Close
ID_011 | Round 1 | Student Attendance report | UI | To download the report download icon is needed | Close
ID_012 | Round 1 | Teacher report | Functional | the teacher is present but still in teacher report its showing absent | Open
ID_013 | Round 2 | Active batch report | Functional | Expired status filter is not functioning | Close
ID_014 | Round 2 | Active batch report | Functional | Without selecting any of the filter should not allow to download the report | Close
ID_015 | Round 2 | Active batch report | Functional | After selecting 2nd and 3rd filters download is not functioning for both | Close
ID_016 | Round 2 | Active batch report | Functional | Select course filter >> after downloading the data is not reflecting in csv file | Close
ID_001 | Round 2 | Active batch report | Functional | By clearing >> it should clear the selected filters data not the list | Close
ID_002 | Round 1 | Active batch report | Functional | Upcoming status filter is not functioning | Close
ID_003 | Round 3 | Bind/Unbind of social login | Functional | If mail id is already linked with diff account should not allow to bind with new account should display proper message as like sign up process | Close
ID_006 | Round 3 | Bind/Unbind of social login | Functional | f user unbind gmail in profile section >> if user try to login with same mail id should not allow to login | Close
ID_007 | Round 3 | Bind/Unbind of social login | Functional | After binding gmail with new account it allowing to bind with fb having diff account there should be some validation | Close
ID_008 | Round 1 | Exam marks reports | Functional | By downloading the section detail report data is not reflecting in csv file | Close |  | P0
ID_009 | Round 1 | Exam marks reports | Functional | By downloading the Question details report data is not reflecting in csv file | Close |  | P0
ID_010 | Round 1 | Exam marks reports | Functional | By default it should not select first exam | Open |  | P2
ID_011 | Round 1 | Exam marks reports | Functional | Quiz and Previous year exam data should not list for reports | Close | Need to test | P0
ID_012 | Round 1 | Exam marks reports | Functional | By selecting the exam only that batch assigned to the exam should be listed (not all the batches of that course ) | Open |  | P0
ID_013 | Round 1 | Student Attendance Report | Functional | For Teacher login in dashboard we are getting 500 | Close
ID_014 | Round 1 | Student Attendance Report | Functional | Sorting icon in reports table was displaying in dev server but not in pp | Open
| Round 1 | Batch wise attendance | Functional | By clicking on Clear month field is not getting clear | Open
| Round 1 | Batch wise attendance | Functional | Although the month is selected but search is not getting enrolled | Open
| Round 1 | Batch wise attendance | Functional | Selecting All filter is not working | Open
| Round 1 | Batch wise attendance | Functional | By clearing the course field search button is still enabled | Open

## QUIZ_BUG LIST
# Id | QA Round | Module | Bug Type | Bug Description | BUG Status | Dev Assign | Dev Status | Priority | Severity
ID_001 | Round 1 | WEB Quiz | Functional | Course dropdown >> should populate only student enrolled courses | Close |  | done | P0
ID_002 | Round 1 | WEB Quiz | Functional | Subject Dropdown should Disabled till course is selected | Close |  | not a bug
ID_003 | Round 1 | WEB Quiz | Functional | Topics are duplicating in topic dropdowns | Close |  | done | P0
ID_004 | Round 1 | WEB Quiz | Functional | If there are no Quiz exams available should not display status with 0 counts should display only message | Close |  | done | P1
ID_005 | Round 1 | WEB Quiz | UI | All Completed status Exam card UI should be as per the design | Close |  |  | P2
ID_006 | Round 1 | WEB Quiz | Functional | After opening summary page if user scroll the page should not scroll the back page | Close |  | Done | P1
ID_007 | Round 1 | WEB Quiz | UI | Exam summary page UI should be as per the design | Phase -2 |  | Phase 2 | P1
ID_008 | Round 1 | WEB Quiz | Functional | Without selecting the subject and topic should not populate the quiz data | Close |  |  | P2
ID_009 | Round 1 | WEB Quiz | Functional | After submitting quiz exam its refreshing all data | Open | should not show default filters |  | P1
ID_010 | Round 1 | WEB Quiz | Functional | Should display unlocked date as routine completed date not the date of exam created | Open |  |  | P0
ID_011 | Round 1 | WEB Quiz | Functional | Even after submitting quiz exam displaying exam under in progress status | Close |  | done | P0
ID_012 | Round 1 | WEB Quiz | Functional | Once the class is complted the exam card is displaying under unlocked list with no data | Close |  | NA | P0
ID_013 | Round 1 | WEB Quiz | Functional | Reattempt is not working | Close |  | done | P0
ID_014 | Round 1 | WEB Quiz | Functional | By closing the exam tab (if user try to resume exam ) >> there should be warning popup , should not close exam directly | Existing bug |  |  | P2
ID_015 | Round 1 | WEB Quiz | Functional | View solution should be there for quiz exam also | Close |  |  | P0
ID_016 | Round 1 | WEB Quiz | Functional | Search should even without enter | Close |  | NA | P2
ID_017 | Round 1 | WEB Quiz | Validation | There should be length validation for the search fields of all 3 dropdowns | close |  | NA | P2
ID_018 | Round 1 | WEB Quiz | UI | Search invalid char and apply filter >> it should not display error message with exam card | Close |  | DONE | P0
ID_019 | Round 1 | WEB Quiz | Functional | There should be cross in the search field inorder to clear the searched text | Close |  | done | P2
ID_020 | Round 1 | WEB Quiz | Validation | There should be length validation for exam search field | Close |  | NA | P2
ID_021 | Round 1 | WEB Quiz | Functional | Time per question timer should be there (its there in apk quizs ) | Phase-2 |  |  | P1
ID_022 | Round 1 | WEB Quiz | Functional | There should be breadcrumbs in the top of the dropdowns | Close |  | done | P1
ID_023 | Round 1 | WEB Quiz | Functional | If the user is defaulter should not get quiz exam | Close |  | DONE | P0
ID_024 | Round 1 | WEB Quiz | Functional | reattemt >> submit the exam its not closing the exam tab | Close |  |  | P0
ID_025 | Round 1 | WEB Quiz | Functional | Free user course should not list in course dropdown (demo ) | Close | Need to remove demo course | DONE | P2
ID_026 | Round 1 | WEB Quiz | UI | while loading the page should not display exam card | Open |  |  | P1
ID_027 | Round 2 | WEB Quiz | UI | Enter invalid char and enter its duplicating error message | Close |  |  | P0
ID_028 | Round 2 | WEB Quiz | Functional | Should not display the quiz data if batch is expired | Close | expired+60days | DONE | P0
ID_027 | Round 2 | WEB Quiz | UI | If there is no quiz should display no data available message section wise also | Open |  | DONE

## Offline & Online Teacher attend
# Id | QA Round | Module | Bug Type | Bug Description | BUG Status | Dev Assign | Dev Status | Priority | Severity
ID_001 | QA Round -1 | Student Attendance report | Functional | Time of class is displaying for offline batch | Close
ID_002 | QA Round -1 | Student Attendance report | Functional | For offline attendance the data in report for columns are mismatching | Close
ID_003 | QA Round -1 | Student Attendance report | Functional | Teacher attendance is also displaying in student report | Open
ID_004 | QA Round -1 | Student Attendance report | Functional | Data for today's class scheduled for offline batch is not displayin | Close
ID_005 | QA Round -1 | Student Attendance report | Functional | Excel report column name and data is not correct | Close
ID_006 | QA Round -1 | Student Attendance report | UI | Date selection UI alignment is not proper | Close
ID_007 | QA Round -1 | Student Attendance report | UI | Date selection box needs to be aligned properly | Close
ID_008 | QA Round -1 | Student Attendance report | Functional | No reports is getting generated for the recent classes though in admin its reflecting in online attendance logs | Close
ID_009 | QA Round -1 | Student Attendance report | Functional | For previous classes also no reports are getting generated | Close
ID_010 | QA Round -1 | Student Attendance report | Functional | If all 4 fields are mandatory to give then search buttin should be disabled | Close
ID_011 | QA Round -1 | Student Attendance report | Functional | If no data is thier the graph should not display (for teacher login) | Open
ID_012 | QA Round -1 | Student Attendance report | UI | Ui for date is breaking | Close
ID_013 | QA Round -1 | Student Attendance report | Functional | If user has searched for a attendance having no data >> after changing its displaying no rec but data is getting downloaded | Close
ID_014 | QA Round -1 | Student Attendance report | Functional | To download the report download icon is needed | Close
ID_015 | QA Round -1 | Student Attendance report | Functional | For Teacher login in dashboard we are getting 500 | Close
ID_016 | QA Round -1 | Student Attendance report | Functional | Sorting icon in reports table was displaying in dev server but not in pp | Open
ID_017 | QA Round -1 | Student Attendance report | Functional | For teacher login we are not getting any data for student attendance report | Open