## Daily Task (hidden)
Team member | [76 empty] | 2023-08-02 | 2023-08-03 | time axis 2023-02-03 to 2023-06-10
Shubhrajyoti | 2023-02-03: ricesmart planning Course discussion rs backend notification payment gateway discussion; 2023-02-06: Ideation on rubrics Discussion on rs extender plan rs app release planning; 2023-02-07: rs internal notification requirements; 2023-02-08: Rs deeplinking RS release QA and notes exam requirement change discussion; 2023-02-09: RS Extender plan Cyclic routine Exam requirement change discussion; 2023-02-10: RS Extender plan and course creation issue Exam requirement change discussion and PRD; 2023-05-22: 1. Website Admin PRD(4 Hours) 2. RICEsmart app review (4 hours); 2023-05-23: 1. Referral proposal Ideation and draft (4 Hours) 2. RICEsmart Ideation (5 hours)
Aman | 2023-02-03: 1. Examination Module Changes Finished. 2. Course Creation User Flow Discussion and changes. 3. Grading Scheme Wireframing Pending.; 2023-02-06: 1. Course Settings 2. Rubrics; 2023-02-08: 1. Examination Flow Demo (Discussing requirements with devs); 2023-02-09: 1. Examination Flow Providing Requirements to the devs. 2. Course User Flow.; 2023-02-10: Editing Exam Requirements; 2023-02-11: Course Discussion; 2023-02-13: Course Discussion Continued; 2023-02-14: Examination discussion with devs; 2023-02-15: Course changes; 2023-02-16: Course Settings; 2023-02-17: Student view of Course; 2023-02-20: Student Course Dashboard; 2023-03-14: 1. Subject Tags in course wireframes 2. Item Hierarchy User Flow wireframes; 2023-03-15: 1. Accounts User Flow Meeting w/ Devs; 2023-03-20: 1. Account Level Master Setup for Course; 2023-03-21: 1. Account Level Master Setup for Course Contd.; 2023-03-22: 1. Hierarchy user flow for adding content in course; 2023-03-23: 1. Hierarchy user flow for adding content in course contd.; 2023-05-22: 1. User Onboarding LMS Review - Left (Server Issue) 2. ATC Website Accgrade Product Page (3 hrs); 2023-05-23: 1. User Onboarding LMS Review - Left (Server Issue) 2. ATC Website Admin Designs (8hrs); 2023-05-24: 1. User Onboarding LMS Review - Left (Server Issue) 2. ATC Website Admin Designs Completed (3 hrs) 3. ATC Website - Blogs Page (3 hrs) 4. Employee landing page for web & mobile (1 hr); 2023-05-25: 1. User Onboarding & Course review in LMS (3 hrs) 2. ATC Website Employee Page Web & Mobile (1hr) 3. LMS Meeting (1 hr); 2023-05-29: ATC Websites Service Pages - 1. Technology Transformation (2 hrs) 2. Cloud Tranformation (2 hrs) 3. Master Data Governance (2hrs) 4. LMS Course Issues (1 hr) 5. Few calls (40 mins); 2023-05-30: 1. Question Bank issues updated in excel (2 hrs) 2. ATC Website Service Pages - - Mobility Solutions ( 1.5 hrs) - Analytics Including SAC (2 hrs); 2023-06-01: Leave; 2023-06-02: Leave; 2023-06-05: Leave; 2023-06-06: Leave | Course Management 1. Modules (Done) 2. People (Pending) 3. Examinations (Pending) 4. Announcements (Pending) 5. Pages (Pending) 6. Settings (Pending) | Course Management 1. Modules (Done) 2. People (Done) 3. Examinations (Done) 4. Announcements (Done) 5. Pages (Done) 6. Settings (Done) | 1. User Management (Admin) 2. Permissions (Admin) 3. Student Dashboard
Onkar | 2023-02-03: Course Module PRD User Story User Flows; 2023-02-06: Course Module PRD User Story User Flows Final Drafting; 2023-02-07: Editing The Final Draft Completion; 2023-02-08: PRD: Creating a Course & Adding Module; adding changes; 2023-02-09: PRD: Creating a Course & Adding Module; adding changes, Rubric; 2023-02-10: Course&Module rubric; 2023-02-13: Course&Module rubric adding modifications Linkedin Post; 2023-02-14: Course&Module rubric adding modifications; 2023-02-15: Course&Module rubric adding modifications Linkedin Post; 2023-02-16: Course&Module rubric adding modifications Presentation Design(All Hands); 2023-02-17: Course&Module rubric adding modifications Flyer preparation; 2023-02-20: Course and module modification Buuzed Video content Preparation: Promotion,Playstore,Inauguration; 2023-02-21: Course and module modification Buuzed Video content Preparation: Promotion,Playstore,Inauguration; 2023-02-22: Course and module modification Buuzed Video content Preparation: Promotion,Playstore,Inauguration; 2023-02-23: Course and module modification Buuzed Video content Preparation: Promotion,Playstore,Inauguration; 2023-02-24: Course and module modification Buuzed Video content Preparation: Promotion,Playstore,Inauguration; 2023-02-27: Course Module PRD Client Meeting Arrangement LinkedIn prospect targeting; 2023-02-28: Course Module PRD Client Meeting Arrangement LinkedIn prospect targeting; 2023-03-01: Course Module PRD Client Meeting Arrangement LinkedIn prospect targeting; 2023-03-02: Course Module PRD Client Meeting Arrangement LinkedIn prospect targeting; 2023-03-03: Course Module PRD Client Meeting Arrangement LinkedIn prospect targeting; 2023-03-06: Course Module PRD Client Meeting Arrangement LinkedIn prospect targeting; 2023-03-07: Course Module PRD Client Meeting Arrangement LinkedIn prospect targeting; 2023-03-08: Course Module PRD Client Meeting Arrangement LinkedIn prospect targeting Social Media Post; 2023-03-09: Course Module PRD Client Meeting Arrangement LinkedIn prospect targeting Social Media Post; 2023-03-10: Course Module PRD Client Meeting Arrangement LinkedIn prospect targeting Social Media Post; 2023-03-14: Course Creation, Course Configuraton,Item hierarchy PRD Social Media Post design Client prospecting; 2023-03-15: Course Creation, Course Configuraton,Item hierarchy PRD Social Media Post design Client prospecting; 2023-03-16: Course Creation, Course Configuraton,Item hierarchy PRD Social Media Post design Client prospecting; 2023-03-17: Course Creation, Course Configuraton,Item hierarchy PRD Social Media Post design Client prospecting; 2023-03-20: Course Module PRD, Facebook Account Creation Client prospect; 2023-03-21: Course Module PRD, Sales Database Update Client prospect; 2023-03-22: Course Module PRD, Sales Database Update Client prospect; 2023-03-23: Course Module PRD, Sales Database Update Client prospect; 2023-03-27: PRD Drafting Master Setup PRD Upwork Account Creation Rocket Reach Account Creation; 2023-03-28: PRD Drafting Master Setup PRD Client Targeting; 2023-03-29: PRD Drafting Master Setup PRD Client Targeting; 2023-05-22: 1. Client Prospecting 2. Website PRD(Admin) Review 3. Content Calendar Preparation; 2023-05-23: 1.client meeting 2.Project Proposal 3. Content Creation Plan Meeting 4. Website Admin PRD review

## Sprint planning (hidden)
Sprint Project Tracker
PROJECT START DATE | 2023-01-30
Sprint | Priority | Start | Finish | Duration | Status | %
Complete
Project Summary | [5 empty] | #DIV/0!
Sprint 1 (Course) |  | 2023-01-30 | 2023-02-06 | 5 days
User enrollment in course
Creation of web pages for course | [5 empty] | 5%
Creation of module for course
Linking of exam, quiz and assignment | [5 empty] | 10%
Outcomes and rubrics
Gradesheet | [5 empty] | 100%
Course configurations
Course import/export configurations
Sprint 2 (Routine management) |  | 2023-02-06 | 2023-02-13 | 5 day(s)
Routine creation
Routine assignment
Attendance module
Sprint 3 (Calendar and reports) |  | 2023-02-13 | 2023-02-20 | 5 day(s)
Calendar
Notification journey
Attendance reports
User enrolment reports
Course enrolment reports
Courses reports
Exam reports
Grading reports
Survey creation/edit/delete
Feedback assignment
Sprint 4 (Student flow) |  | 2023-02-20 | 2023-02-27 | 5 days
Account view
Course view
Exam view
Calendar view
Profile
Sprint 5 (Teacher flow) |  | 2023-02-27 | 2023-03-06 | 5 days
Account view
Course view
Exam view
Calendar view
Profile
Sprint 6 (Design system) |  | 2023-03-06 | 2023-03-13 | 5 days
Top bar, Hamburger and settings
End to end design validation
Sprint 7 (Design system) |  | 2023-03-13 | 2023-03-20 | 5 days
Component creation
Sprint 8 (Design system) |  | 2023-03-20 | 2023-03-27 | 5 days
Guidelines for each module

## Gantt Chart (hidden)
| Nalanda | [5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
| Project Start Date: | 2023-01-23 | [5 empty] | January | [13 empty] | February | [27 empty] | March | [30 empty] | April
| Scrolling Increment: | 0 | time axis 2023-01-23 to 2023-04-07
| Task description | Category | Assigned to | Progress | Start | Days | Hours | time axis 2023-01-23 to 2023-04-07
Course Wireframing
1 | Courses dashboard | Goal | Aman | 100% | 2023-01-23 | 1 |  | 2023-01-23: 2
2 | Course terms | Goal | Aman | 100% | 2023-01-23 | 1 |  | 2023-01-23: 2
3 | Course creation | Goal | Aman | 100% | 2023-01-24 | 1 |  | 2023-01-24: 2
4 | Course Modules | Goal | Aman | 100% | 2023-01-25 | 3 |  | 2023-01-25: 2; 2023-01-26: 2; 2023-01-27: 2
5 | Announcement | Goal | Aman | 100% | 2023-01-24 | 1 |  | 2023-01-24: 2
6 | Grading | Goal | Aman | 100% | 2023-02-01 | 4 |  | 2023-02-01: 2; 2023-02-02: 2; 2023-02-03: 2; 2023-02-06: 2
7 | Rubrics | Med Risk | Aman | 100% | 2023-01-30 | 2
8 | Setting | On Track | Aman | 100% | 2023-02-03 | 1
9 | Syllabus | High Risk | Aman | 100% | 2023-02-07 | 1
10 | Homepage | Goal | Aman | 100% | 2023-02-03 | 1 |  | 2023-02-03: 2
11 | People | Med Risk | Aman | 100% | 2023-02-03 | 3
12 | Course ideation | Low Risk | Shubhrajyoti | 100% | 2023-01-23 | 7
13 | Course PRD | High Risk | Shubhrajyoti | 20% | 2023-01-31 | 5
| Course demo | High Risk | Shubhrajyoti |  | 2023-02-08 | 1 | 2
Exam
Routine
| Dashboard |  | Aman | 100% | 2023-02-09 | 1
| Routine creation |  | Aman | 100% | 2023-02-10 | 1
| Routine assignment |  | Aman | 100% | 2023-02-11 | 1
| Attendance |  | Aman | 100% | 2023-02-12 | 1
| Routine Ideation |  | Shubhrajyoti |  | 2023-02-13 | 4 | 2+2+2+2
| Routine PRD |  | Shubhrajyoti |  | 2023-02-14 | 2 | 8+8
Calendar & Notification
| Ideation |  | Shubhrajyoti
| Calendar wireframes |  | Aman | 100%
| Notification Journey |  | Shubhrajyoti
| Notification wireframes |  | Aman
| PRD |  | Onkar |  | 2023-02-09 | 2 | 8+8
| Demo |  | Onkar |  | 2023-02-14 | 2 | 8+8
Admin Report
| Course publish progress ideation |  | Shubhrajyoti |  | 2023-02-13 | 1
| Course assessments ideation |  | Shubhrajyoti |  | 2023-02-13 | 1
| Course activity progress ideation |  | Shubhrajyoti |  | 2023-02-14 | 1
| Account activity ideation |  | Shubhrajyoti |  | 2023-02-14 | 1
| Course publish progress WF |  | Aman |  | 2023-02-14
| Course assessments WF |  | Aman
| Course activity progress WF |  | Aman
| Account activity WF |  | Aman
| PRD |  | Shubhrajyoti |  | 2023-02-17 | 2
Teacher reports
| Attendance ideation |  | Shubhrajyoti |  | 2023-02-21 | 1
| Student activity ideation |  | Shubhrajyoti
| Student performance ideation |  | Shubhrajyoti
| Attendance WF |  | Aman |  | 2023-02-21 | 1
| Student activity WF |  | Aman
| Student performance WF |  | Aman
| PRD |  | Onkar |  | 2023-02-21 | 5
Student reports
| Grade Progression ideation |  | Shubhrajyoti
| Course performance ideation |  | Shubhrajyoti
| Grade Progression WF |  | Aman
| Course performance WF |  | Aman
| PRD |  | Onkar
Student Flow
| Course WF |  | Aman | 100% |  | 3
| Exam |  |  | 100% |  | 2
| Calendar |  |  |  |  | 1 | 4
| Routine |  |  | 100% |  | 1 | 4
To add more data, Insert new rows ABOVE this one

## Project plan (hidden)
Sl. No. | Tasks | Start date | End date
1 | User research | 2022-10-25 | 2022-11-11
2 | Open source research | 2022-10-17 | 2022-10-28
3 | Competitor research | 2022-11-14 | 2022-11-25
4 | Define Macro module | 2022-11-14 | 2022-11-23
4 | Define Business requirement | 2022-11-24 | 2022-11-28
5 | Define MVP | 2022-11-29 | 2022-12-02
| Design guidelines | 2022-11-24 | 2022-12-02
| Breakdown Macro module into smaller goals | 2022-11-24 | 2022-12-02
| LoFi wireframe | 2022-12-05 | 2022-12-09
6 | Create GTM strategy
7 | Create requirement for phase 1 devlopment | 2022-12-12 | 2022-12-23
8 | Development for Phase 1
9 | QA for phase 1 devlopment
10 | Create Requirement for phase 2 devlopment
11 | Development for Phase 2 | 2022-12-26 | 2023-01-13
12 | QA for phase 2 devlopment
13 | Create Requirement for phase 3 devlopment
14 | Development for Phase 3 | 2023-01-16 | 2023-01-27
15 | End to end QA
16 | Beta testing - 2 weeks
17 | Alpha testing - 2 months
18 | Phase-4 Development

## Features (hidden)
Sl. No. | Module | Features | Details | Status | Priority | PRD Date
1 | User management | Roles and permissions | Custom user role can be defined based on permissions and user properties | Done | P1 | 2022-12-19
2 | User management | Custom/mandatory user profile fields | Fields at registration can be configured to be mandatory or optional. Additional fields can be added via an extension plugin. | Later phases | P1 | 2022-12-19
3 | User management | User creation | User can be created in the system based on set of user properties | Done | P1 | 2022-12-19
4 | User management | SSO (Single Sign On) | Third party authentication can be integrated with different type of providers such as SAML, OAuth 2.0 (Facebook, Google, Microsoft, LinkedIn, Github). | Later phases | P1 | 2022-12-19
5 | User management | Other authorization | Email and phone OTP based login, ID-password based authorization | Phase 1 | P1 | 2022-12-19
6 | User management | Self-registration capability | The platform can be configured for users to be able to register themselves. | Later phases | P1 | 2022-12-19
7 | User management | Invitation only | Learners can be invited to a course and receive a link to register in the platform. | Phase 1 | P1 | 2022-12-19
8 | User management | Integration to ERP | Fee payment and other user information can be fetched from ERP | Later phases | P1 | 2022-12-19
9 | User management | Instructors/tutors can be assigned to a subset of learners | Learners can be added to a cohort, and course content can be displayed or hidden based on a cohort. Instructors are able to see all the cohorts. | Inprogress | P1 | 2022-12-19
10 | User management | Act as user | Allows to browse the platform as one user | Later phases | P1 | 2022-12-19
11 | Account management | Account creation | Account can be created for grouping users in set and subset | Done | P1 | 2022-12-19
12 | Account management | Organisational hierrachy | Accounts can be created with parent-child schema where child inherits parent properties. | Done | P1 | 2022-12-19
13 | Account management | Outcomes | Outcomes can be defined for an account | Not Done | P1 | 2022-12-19
14 | Account management | Rubric | Rubrics can be configures for an account | Not Done | P1 | 2022-12-19
15 | Account management | Grading | Grading can be defined for an account | Not Done | P1 | 2022-12-19
16 | Account management | Term | Term is defined for an account. | Phase 1 | P1 | 2022-12-19
17 | Account management | Course | Course is created and assigned to an account | Done | P1 | 2022-12-19
18 | Account management | Organization branding | Needs to be customised through main/top account. All child reflects the branding along their own account branding | Phase 1 | P2
19 | Account management | Sub-account branding | Theme can be customized via changes in the templates and styles. | Phase 1 | P2
20 | Account management | Custom branding | Custom domain (URL) | Phase 1 | P2
21 | Course management | Course enrolment | Instructors can batch enroll learners in a course by a list of emails or user names. | Phase 1 | P1 | 2023-02-06
22 | Course management | Instructor and Teaching assistant enrolment | Instructor needs to be asssigned during course creation. Later multiple instructor or other teaching related roles can be added | Phase 1 | P1 | 2023-02-06
23 | Course management | Guest access settings | Courses can partially be made available for guest access. | Later phases | P2
24 | Course management | Survey enrollment (based on a response) | Courses can have entrance exams and be configured so that only learners who pass the exam are able to access the course. | Later phases | P1 | 2023-02-06
25 | Course management | Invitation only | Courses can be configured to be invitation only. |  | P1 | 2023-02-06
26 | Course management | Course prerequisites control | Course enrolment configuration based on successful completion of one or many courses | Later phases | P2
27 | Course management | Self-enrollment capability | Learners can self-enroll to the courses (such as electives) that are configured. | Later phases | P1 | 2023-02-06
28 | Course management | Leaner activity tracking/monitor learner progress | Progress is monitored as measured by grades and by the completion of each of the course components. | Phase 1 | P1 | 2023-02-06
29 | Course management | Configure rubrics for manually graded exercises | Configurable rubrics are available for peer-graded and staff-graded exercises. | Later phases | P1 | 2023-02-06
30 | Course management | Import/export courses | Courses can be exported and imported from a native format (QTI). | Later phases | P1 | 2023-02-06
31 | Course management | Course validity | Course can be configured for a term with start time and end time | Phase 1 | P1 | 2023-02-06
32 | Course management | Certificate management | Templates can be created and configured by organization and by language. Fields in the template can be overwritten per course. | Later phases | P2
33 | Course management | Certificate management | Bulk generation of certificates | Later phases | P2
34 | Course management | Certificate management | Revoke certificates | Later phases | P2
35 | Course management | Certificate management | Certifications can be downloaded as pdf | Later phases | P2
36 | Course management | Certificate management | Certifications can be easily shared in social networks | Later phases | P2
37 | Course management | Wiki pages | Wiki pages can be used for articles, course outlines, FAQs, and information specific to the units and components. | Later phases | P2
38 | Course management | Courses can be scheduled for automated release | The entire course can be automatically published at a specific date in the future. | Done | P1 | 2023-02-06
39 | Course management | Allows instructors to create engaging learning sequences | Learning sequences can be created and organized into a structure of sections and subsections. | Done | P1 | 2023-02-06
40 | Course management | Preview before publishing | Facilitates the review of content to avoid publishing errors. | Phase 1 | P1 | 2023-02-06
41 | Course management | Content restricted, based on dates | Each section or subsection in a course can be automatically published at a specific date in the future. | Phase 1 | P1 | 2023-02-06
42 | Course management | Due dates for specific components can be set | Due dates/times are supported for graded subsections. They are displayed to learners in their local time zones. | Phase 1 | P1 | 2023-02-06
43 | Course management | Course contents reusability | Course sections, subsections, and components can be easily duplicated and moved for re-use in other parts of the course. This saves time, since the content does not have to be re-built from scratch. | Phase 1 | P1 | 2023-02-06
44 | Course management | Author checklists for course readiness | Checklists help course staff ensure courses are fully ready before launching them. | Not Done | P2
45 | Content management | Platform supports the creation of content libraries | Content libraries allow for the re-use of content in multiple courses and for the random drawing of content from a library into a course. | Done | P1 | 2023-02-06
46 | Content management | Multi-user authoring capability | Team work is facilitated. Many authors can work simultaneously in the same library. | Inprogress | P1 | 2023-02-06
47 | Content management | Questions bank | Library of different question types can be made as library | Done | P1 | 2023-02-06
48 | Content management | CMS integrations | Can integrate with CMS/marketing website (WordPress, Drupal, etc.) and display user information, course catalog, enrollment status. | Done | P1 | 2023-02-06
49 | Content management | Ecommerce | Ecommerce page can be created for courses | Later phases | P3
50 | Content management | Native CMS capabilities | Availability to publish content outside of the courses, for example on the homepage, additional pages, etc. via modification of the templates. | Not Done | P1 | 2023-02-06
51 | Content management | Rich text format support | bold, italics, bullet etc | Done | P1 | 2023-02-06
52 | Content management | Mathematical equation and symbol support |  | Inprogress | P1 | 2023-02-06
53 | Content management | Scorm and XAPI content support |  | Later phases | P1 | 2023-02-06
54 | Content management | LTI protocol (learning tools interoperability) | Platform should act as an LTI consumer and also as an LTI provider. | Later phases | P1 | 2023-02-06
55 | Content management | Formats supported for learning content | PPTs, PDFs, and other similar content formats. Video support, Vimeo and Youtube video intergration. | Inprogress | P1 | 2023-02-06
56 | Exam management | Exam configurations | Several problem types are available for authors to build activities and improve learning. Available with multiple configuration options, error tolerance, randomization, limited number of attempts, time between attempts, response visibility controls, etc. This allows for easy course creation, as well as diversified courses for learners. | Done | P1 | 2023-01-20
57 | Exam management | Question types | MCQ, Fill in the blanks, multiple choice, match the following, short text response, numeric response, objective questions/open-response/file submission,Visual drag and drop | Done | P1 | 2023-01-20
58 | Exam management | Peer graded questions | Grading for open-response questions can be configured with a customizable rubric and can be performed by the learners themselves, other peers, the instructors, or any combination. | Later phases | P3
59 | Exam management | Number of attempts control |  | Done | P1 | 2023-01-20
60 | Exam management | Show response control | The feedback and problem solution display can be shown or hidden per problem. | Later phases | P1 | 2023-01-20
61 | Exam management | Show hint |  | Not Done | P1 | 2023-01-20
62 | Exam management | Show correctness control | The correctness can be shown or hidden per problem. | Not Done | P1 | 2023-01-20
63 | Exam management | Randomize problems | Problems can have built-in randomization, so that they have a variable set of parameters for learners. | Later phases | P1 | 2023-01-20
64 | Exam management | Randomly pulling problems from a question bank. | Question banks to create randomized assessments within the courses. | Done | P1 | 2023-01-20
65 | Exam management | Annotation toll for assessing open-response questions | Annotation tool with rubric configuration should be available to assess an open-respose question | Phase 1 | P1 | 2023-01-20
66 | Exam management | Proctored exams | Using external tools and services, exams can be configured to be proctored. | Not Done | P2
67 | Exam management | Exam process management | seating arrangement, admit card, exam enrollement, exam fee | Not Done | P2
68 | Exam management | Time control in exam | To control resume capabilities of timed exam and set set exam with time control | Done | P1 | 2023-01-20
69 | Social learning tools | Polls in which the student can reply to a given question and then see the aggregated responses from the group | A poll component is available, with the option to either display or not display the aggregated responses to learners. | Later phases | P2
70 | Social learning tools | Word cloud | Submit ideas or examples and have them listed in text walls, word clouds or similar visualizations | Later phases | P2
71 | Social learning tools | Discussions forum | Course participants can engage in active discussions, which can be organized both as part of a course unit, and as course wide discussions. There are many configuration, management and moderation options for discussions. | Later phases | P2
72 | Social learning tools | bookmark course content | Learners can add personal bookmarks to specific course units. Bookmarks will be displayed in the specific unit and also aggregated in a list with the corresponding links. | Later phases | P1 | 2023-02-06
73 | Social learning tools | Student notes | Learners can add personal notes to specific course components. Student notes can be hidden/shown within a specific unit and also aggregated in a list with corresponding links. | Later phases | P2
74 | Routine management | Routine creation/edit/delete | Routine can be created for a course. It can be mapped to a instructor and content of the course | Inprogress | P1 | 2023-02-13
75 | Routine management | Routine assignment | Routine can be assigned to one user of course, a groupof the course, a section of the course or to all the members of the course. | Inprogress | P1 | 2023-02-13
76 | Routine management | Automated routine | Baseed on the course, the assigned instructor and time slots, automated routine schedule can be created. | Inprogress | P1 | 2023-02-13
77 | Routine management | Common routine | Same routine can be applied to more than one course | Phase 1 | P1 | 2023-02-13
78 | Routine management | Attendance | Particitating user can mark their attendance during a live class. | Phase 1 | P1 | 2023-02-13
79 | Ticketing system | Ticket creation/edit/delete | Users will be able to create tickets for support to based on their grievance | Later phases | P2
80 | Ticketing system | Ticket assignment | Ticket can be autimatically assigned based on the issue or can manually assign to a support user. | Later phases | P2
81 | Ticketing system | Chatbot | Chatbot integration to solve the user query |  | P2
82 | Calendar and notification | Automated notification | Automated notification can be created for events course publishing, Class routine, exam notification etc. | Later phases | P1 | 2023-02-20
83 | Calendar and notification | Notificaition delivery system | Notifications can be delived on web, in mobile app as SMS or as an email. | Later phases | P1 | 2023-02-20
84 | Calendar and notification | Calendar | Shows all the upcoming and past event of an user | Phase 1 | P1 | 2023-02-20
85 | Calendar and notification | Mass email | Mass email for an account or course users | Phase 1 | P1 | 2023-02-20
86 | Calendar and notification | Notification dashboard | Make available a notification dashboard for students so that they can review their alerts and announcements. | Phase 1 | P1 | 2023-02-20
87 | Video-conferencing | Video/audio streaming | Upto 150 participants | Later phases | P2
88 | Video-conferencing | Whiteboard | To collaborate or to stream a file/video | Later phases | P2
89 | Video-conferencing | Polls | To quiz and see leaderboard rank of a class | Later phases | P2
90 | Video-conferencing | Comment | For textual interactions | Later phases | P2
91 | Reports | Attendance |  | Phase 1 | P1 | 2023-02-20
92 | Reports | User enrolment |  | Done | P1 | 2023-02-20
93 | Reports | Course enrolment |  | Done | P1 | 2023-02-20
94 | Reports | Courses |  | Inprogress | P1 | 2023-02-20
95 | Reports | Exam marks |  | Later phases | P1 | 2023-02-20
96 | Reports | Grading |  | Later phases | P1 | 2023-02-20
97 | Feedback | Survey creation/edit/delete |  | Later phases | P1 | 2023-02-20
98 | Feedback | Feedback assignment |  | Later phases | P1 | 2023-02-20
99 | Search | Search capability | User can search course content or any other link using single search option | Later phases | P1
100 | Student |  | Student flow | Inprogress | P1 | 2023-03-06
101 | Teacher |  | Teacher flow | Inprogress | P1 | 2023-03-06
102 | Design system |  | Components |  | P1 | 2023-03-27
103 | Design system |  | Brand guidelines |  | P1 | 2023-03-27

## Proposed macro Modules (hidden)
Modules | #1 | #2 | #3 | #4 | #5 | #6 | #7 | #8
User management | Admin creates user | custom user properties as set by admin | Login module with Oauths for user (student + teacher) | Admin can create role | Admin assigns role to user | Define view and permission for each role
Account management | Admin can create account and sub accounts to define org hierrarchy | Map users to accounts | Admin can create role | Admin assigns role to user
Course | Course is created by admin | Teacher creates the modules in the course | Teacher can create assignment | Teacher can create quizzes | Teacher can create custom rubric for course
Routine management | Admin adds student user to batch | courses are assign to batch by admin | Teacher creates class and maps it to course | Attendance is generated for student | Student can rate teacher and class | Admin can monitor class quality
Exam management | Admin creates exam for a batch | Exam question are mapped to skills | Exam skills are mapped to a custom rubric | Analytics and grade is generated | certificate is generated | Teacher can check subjective paper.
Calendar | User can create own events | Students and teacher can see assessment deadline, exams and classes | Student can see announcements
Discussion | Threads where Teacher and student can engage in discussions
Video conferncing | live class integration with course and Routine

## Canvas modules (hidden)
Sl. No | Module | Sub-Module | User | Feature/Functionality | User Story
1 | Course | Dashboard/Homepage |  | Homepage will give a broad overview and introduction to the course | e.g. course name, about the course, instructors, assessment overview etc.
2 | Course | Dashboard/Homepage |  | Dashboard will show a side bar with tabs to all the sub-functionalities or sub-features of the course
3 | Course | Dashboard/Homepage |  | Homepage will show the latest annoucements made with regards to the course
4 | Course | Dashboard/Homepage |  | Homepage will show the upcoming deadlines and submissions due for the course
5 | Course | Dashboard/Homepage |  | Homepage will show the schedule of live classes - Completed (recorded), Currently going on, and Upcoming
6 | Course | Dashboard/Homepage |  | Homepage Assessment/submission summary.
7 | Course | Dashboard/Homepage |  | Homepage will show a progress percentage of the course
8 | Course | Dashboard/Homepage |  | Homepage will show the schedule of classes allocated to the particular course
9 | Course | Dashboard/Homepage |  | Homepage will show recently visited content or chapter or recently participated exam and when to expect result.
10 | Course | Syllabus |  | Syllabus will show topic wise or module wise daily breakdown of classes
11 | Course | Syllabus |  | Syllabus will show overview of Course Plan and Course coverage
12 | Course | Syllabus |  | Syllabus will show detailed description of the Assignments set, details of deliveravles, due date, etc.
13 | Course | Modules |  | Create Modules, Submodules, Sections or Subsections
14 | Course | Modules |  | Ability to set lock/unlock modules or submodules based on necessary dates for automated release/publish
15 | Course | Modules |  | Ability to add a pre-requisite to a module/submodule in order to progress with the course
16 | Course | Modules |  | Ability to publish or unpublish a course/module/sub-module/quiz/assessments etc.
17 | Course | Modules |  | Ability to view progress summary of the course
18 | Course | Modules |  | Ability to add content files, pages, pdf, docx, image files, external files etc
19 | Course | Modules |  | Ability to add Quiz, Assignments, Project, Homework
20 | Course | Modules |  | All the Modules, Submodules, Assignments, Content etc. will be referred to by a Heading Name
21 | Course | Modules |  | Ability to Edit the Heading Name
22 | Course | Modules |  | Ability to duplicate Modules, Submodules, Assignments, Content etc.
23 | Course | Modules |  | Ability to exchange Modules, Submodules, Assignments, Content etc between 2 different Courses | E.g. one assignment of a pariticular module from Course A can be copied to another module of Course B
24 | Course | Modules |  | Ability to Edit, Delete, Copy, Import, Export Modules, Submodules, Assignments, Content etc.
25 | Course | Modules |  | Ability to Download Course Content, Assignments etc and Submit solutions
26 | Course | Modules |  | Ability to review and audit course by colleagues, or higher authority
27 | Course | Modules |  | Ability to Preview Course before Publishing
28 | Course | Modules |  | Author checklists for course readiness | Checklists help course staff ensure courses are fully ready before launching them.
29 | Course | Modules |  | Ability to schedule Live Classes within modules | Assign the class to a batch, course or manually choosen group of students
30 | Course | Modules |  | Ability to restrict/schedule content or assignments visibility based on dates
31 | Course | Modules |  | Ability to bookmark course section/subsection in dashboard
32 | Course | Modules |  | User will be able to take notes in each sub-section
33 | Course | Modules |  | User will be able to leave notes in the video for specific timestamp
34 | Course | Modules |  | user will be able to leave public/private note to highlight important points (highlight+comment)
35 | Course | Modules |  | User will be able to rate/give feedback(stars) to sub-section
36 | Course | Modules |  | Ability to restrict/schedule content or assignments visibility based on dates
37 | Course | Modules |  | User can search for specific content inside the course
38 | Course | Modules |  | User can add timestamps in the videos of the course for ease of usability
39 | Course | Announcements/Newsfeed |  | Show all Course specific annoucements posted by teacher, admin or any authoritiries | Ideally sorted by date of posting
40 | Course | Announcements/Newsfeed |  | Specify annoucements that have been read and unread
41 | Course | Announcements/Newsfeed |  | Show number of views and who viewed the annoucements
42 | Course | Announcements/Newsfeed |  | Ability to delete annoucements (with confirmation)
43 | Course | Announcements/Newsfeed |  | Ability to add comments to annoucements
44 | Course | Announcements/Newsfeed |  | Ability to like/unline/forward/share announcements between peers
45 | Course | Announcements/Newsfeed |  | Ability to create new annoucements - with Title, Text Editor, Attachments etc.
46 | Course | Announcements/Newsfeed |  | Ability to specify with whom to share the annoucements - individual student, batch, course level
47 | Course | Announcements/Newsfeed |  | Option to pre-schedule a date and time to post annoucement
48 | Course | Announcements/Newsfeed |  | Ability to comment on announcements and engage into conversations
49 | Course | Announcements/Newsfeed |  | Ability to search specific old annoucements by name, date or keywords
50 | Course | Assignments |  | Ability to set Assignments as part of a Course/Module
51 | Course | Assignments |  | Ability to mention weightage of each assessment | Weightage should sum upto 100%
52 | Course | Assignments |  | Ability to create a group of Assignments under one single assessment | Under one assignment (e.g. total 50 marks) we can add multiple assessments (each of 10,10,10,20 marks)
53 | Course | Assignments |  | Ability to mention Assignment name and description (using text editor)
54 | Course | Assignments |  | Ability to mention full marks to the questions, tasks, assignments, sub tasks | Whatever task or sub-task is set should be able to set full marks to it
55 | Course | Assignments |  | Ability to display marks as points, percentage, gpa etc.
56 | Course | Assignments |  | Ability to allow solution submission to questions directly using text editor
57 | Course | Assignments |  | Ability to submit solutions as File uploads, external links etc.
58 | Course | Assignments |  | Ability to restrict type of file submissions allowed
59 | Course | Assignments |  | Specify number of submissions or attempts allowed
60 | Course | Assignments |  | Ability to set due dates to assignments
61 | Course | Assignments |  | Ability to set availability dates or visibility dates of assignments
62 | Course | Assignments |  | Ability to set assignment to individual students, group of students, batch, module or course level
63 | Course | Assignments |  | Ability to assign assignment as a group assignment | Students can be graded as a group, or individually based on their contribution to the group assignment
64 | Course | Assignments |  | Ability to Publish or Unpublish assignments
65 | Course | Assignments |  | Ability to Save, Copy or Delete assignments
66 | Course | Assignments |  | Ability to modify due dates or submission dates of assignments before any submission has been made
67 | Course | Assignments |  | Ability to add a Rubrics or marking scheme to the assignment
68 | Course | Assignments |  | Ability to peer-review and grade submissions | Assign peers manually or automatically, and peers could be anonymous
69 | Course | Assignments |  | Ability to submit feedback to solutions or add auto-feedback
70 | Course | Assignments |  | Ability to download submissions for marking
71 | Course | Assignments |  | Ability to upload marked submissions with feedback
72 | Course | Assignments |  | Ability to share assignments between Courses, Modules
73 | Course | Assignments |  | Ability to view assignments before publishing | Student View
74 | Course | Quiz |  | Ability to set Quiz Exercises as part of the Modules
75 | Course | Quiz |  | Quiz questions can be set from questions within Question Bank
76 | Course | Quiz |  | Ability to mention weightage of each quiz
77 | Course | Quiz |  | Ability to create a group of Quizzes under one single quiz
78 | Course | Quiz |  | Ability to mention Quiz name and description (using text editor)
79 | Course | Quiz |  | Ability to choose between graded or ungraded quiz or practice quiz
80 | Course | Quiz |  | Ability to add Quiz to an already created Assignment as part of a Module
81 | Course | Quiz |  | Ability to set time limit to a Quiz
82 | Course | Quiz |  | Ability to specify number of attempts allowed for the quiz
83 | Course | Quiz |  | Ability to view responses after submission, and whether correct or incorrect was done after it has been assessed
84 | Course | Quiz |  | Ability to show correct answers on immediate submission, or after certain date has passed, or once marks/solution released
85 | Course | Quiz |  | Ability to set availability dates or visibility dates of a quiz
86 | Course | Quiz |  | Ability to set due dates to Quiz submissions or participation
87 | Course | Quiz |  | Ability to shuffle questions/answers of a particular quiz
88 | Course | Quiz |  | Ability to link quiz to a Question Bank from which questions can be pulled randomly or based on conditions
89 | Course | Quiz |  | Ability to add Rubrics or Marking scheme for a quiz
90 | Course | Quiz |  | Ability to edit a quiz before it has started/while it is running
91 | Course | Quiz |  | Ability to Add questions to a quiz - MCQ, T/F, Fill in the blanks, Fill in multiple blanks, Multiple Answers, Matching, File Upload, Formula based question
92 | Course | Quiz |  | Quiz can also be in the form of a Survey i.e. Ungraded quiz that can be shared with students
93 | Course | Quiz |  | For Multiple Choice Questions - ability to set the possible answer choices and correct answer (in the backend)
94 | Course | Quiz |  | For Multiple Choice Questions - ability to attach automated feedback to the choosen answer on submission
95 | Course | Quiz |  | For True/False Questions - ability to set the possible answer choices and correct answer (in the backend)
96 | Course | Quiz |  | For Fill in the Blanks Questions - ability to set the possible answer choices and correct answer (in the backend)
97 | Course | Quiz |  | For Fill in the Blanks Questions - ability to show where the blank answer/multiple blank answers needs to be inputted
98 | Course | Quiz |  | For Numerical Answer questions - ability to set the possible answer choices and the correct answer (some precision can be allowed)
99 | Course | Quiz |  | Abilityt to set formula based questions e.g. What is 5+x?
100 | Course | Quiz |  | Ability to preview a Quiz and quiz questions before publishing
101 | Course | Quiz |  | Ability to participate in a preview quiz - showing start date, time elapsed, time remaining, submission time etc.
102 | Course | Quiz |  | Ability to submit quiz and see solutions immediately or once released by teacher, and see marks immediately or once release by teacher
103 | Course | Quiz |  | Protect a quiz with an access code to determine who is allowed to participate in the quiz
104 | Course | Quiz |  | Show attempt history of a Quiz
105 | Course | Quiz |  | Ability to restrict quiz submission after deadline has passed
106 | Course | Quiz |  | Ability to view student progress of the quiz, number of attempts taken, time taken, marks scored etc
107 | Course | Quiz |  | Ability to grant students extra attempts, grant extra time for timed quizzes, and manually unlock quiz attempts.
108 | Course | Quiz |  | Ability to lock questions after answering.i.e. cannot return to the previous question once it has been answered.
109 | Course | Quiz |  | Ability to send message to students who have not submitted the quiz
110 | Course | Quiz |  | Ability to Lock quiz before deadline
111 | Course | Quiz |  | Enable proctoring during Live Quiz or Assignments e.g. lockdown browser, face recognition etc.
112 | Course | Quiz |  | Coding solution as assignment
113 | Course | Quiz |  | Ability to regrade an assignment or quiz, once originally graded, published or released
114 | Course | Discussion |  | Ability to start a Discussion thread for a Course, Module, Sub-Module, Event, Exam-related, Chapter, Topic anything etc.
115 | Course | Discussion |  | Ability to set a name and text of the Discussion using Text Editor
116 | Course | Discussion |  | Ability to set whom to post the Discussion for - Batch Level, Course Level, or assign it to manually created groups
117 | Course | Discussion |  | Ability to post a file attachment with a Discussion
118 | Course | Discussion |  | Allow threaded replies to the Discussions
119 | Course | Discussion |  | Allow Like, Unlike, UpVote, DownVote of a Discussion and the threaded comments - similar to reddit
120 | Course | Discussion |  | Ability to show details of Discussions - time and date posted, number of replies, how many people and who has seen, when does discussion expire etc.
121 | Course | Discussion |  | Allow Group Discussions i.e. discussions can be participated in groups
122 | Course | Discussion |  | Ability to Edit, Delete posted discussions and comments
123 | Course | Discussion |  | Ability to Publish, Unpublish, Lock and Unlock discussions
124 | Course | Discussion |  | Ability to send notifications when discussions have new comments, replies and also ability to tag users of the thread when replying
125 | Course | Discussion |  | Ability to share Discussions between courses
126 | Course | Discussion |  | Ability to allow, disallow comments to discussions
127 | Course | Discussion |  | Ability to duplicate a discussion within a course
128 | Course | Discussion |  | Ability to send Discussion to another instructor
129 | Course | Discussion |  | Ability to assign discussions which can be graded individually or as a group
130 | Course | Discussion |  | Ability to assign peer reviews to a discussion
131 | Course | Discussion |  | Ability to attach files to a discussion
132 | Course | Enrollments |  | Ability to see the students, teachers, observers, TA etc. assigned to a Course
133 | Course | Enrollments |  | Ability to add or remove students to a course or batch manually or in bulk
134 | Course | Enrollments |  | Ability to create Group of students within a single course
135 | Course | Enrollments |  | Ability to allow self-sign-up to groups
136 | Course | Enrollments |  | Ability to send notifications to students when assigned to groups or a new group
137 | Course | Enrollments |  | Ability to restrict group membership based on requirements
138 | Course | Enrollments |  | Ability to delete a group or remove members of a group
139 | Course | Enrollments |  | Ability to send/resend invitations to students to be added to a Course or Groups
140 | Course | Enrollments |  | Ability to view student details added to a course
141 | Course | Enrollments |  | Ability to view attendance details or participation details of a student in a Course
142 | Course | Enrollments |  | Ability to edit access roles of users attached in the Course
143 | Course | Pages |  | Pages will be the Content part of the Course
144 | Course | Pages |  | Ability to create a new Page and add it to a Course Module or sub-module or examination
145 | Course | Pages |  | Ability to add a Title to the Page
146 | Course | Pages |  | Ability to add content of all sorts to the Page - text, images, tables, mathematica equations. latex, documents, external links etc.
147 | Course | Pages |  | Ability to set permission who can create or edit content of the page
148 | Course | Pages |  | Ability to set a Page as the Front Page of a course as Course description page
149 | Course | Pages |  | Ability to Share, Copy, Duplicate, Edit and Delete Pages - to other courses, or modules
150 | Course | Pages |  | Ability to see Revision History of a page
151 | Course | Pages |  | Ability to Publish or Unpublish a page as part of a Course, Module or Sub-module
152 | Course | Pages |  | Ability to view the page as a Student
153 | Course | Pages |  | Ability to view all pages (Index) as part of the Course - and details such as Name, creation date, published or not, edit history etc., and also can create/delete page
154 | Course | Pages |  | Ability to sort pages based on filter or conditions
155 | Course | Pages |  | Ability to support real-time communication/live-classes/virtual-classrooms
156 | Course | Pages |  | Ability to support H5P components, SCORM content, XAPI content
157 | Course | Pages |  | LTI protocol (learning tools interoperability)
158 | Course | Outcomes |  | Ability to specify Learning Outcomes of a course
159 | Course | Outcomes |  | Outcomes are created to track mastery in a course. | E.g. meets expectation - 5 marks, exceeds expectations - 10 marks, does not meet expectation - 0 mark
160 | Course | Outcomes |  | Ability to specify an outcome name, description and criterion to meet the outcome, and clearly indicate how and when the criterion will be fulfiled
161 | Course | Outcomes |  | Ability to tag a created Outcome to a course, module, assignment, exam, coursework, quiz etc.
162 | Course | Outcomes |  | Ability to Align outcomes to Question Bank
163 | Calender |  |  | Ability to see a calender of the year/term by days, months or year
164 | Calender |  |  | It will show university level events, course specific events, important deadlines, due dates, exams
165 | Calender |  |  | Ability to integrate Calender with Google Calendar, iCal, Outlook, etc
166 | Calender |  |  | Ability to filter calender view by course
167 | Calender |  |  | Ability to add events - both teacher side and student side (other roles). User can add other user to the event.
168 | Calender |  |  | Ability to pre-schedule events and set reminder/alerts
169 | Calender |  |  | Ability to publish or unpublish events
170 | Calender |  |  | Specify event type when adding to calender - e.g. can be a special class event, assignment due date, TODO, group events etc.
171 | Calender |  |  | Calendar will have list view and grid view
172 | Calender |  |  | User will be able to duplicate event
173 | Calender |  |  | Calendar will be linked to routine management system
174 | Calender |  |  | User will be able to share and view shared calendar
175 | Calender |  |  | Ability to schedule recurrent office hours, and assign it to specific batch or group of students, and automatically gets added to the relevant calender feed
176 | Calender |  |  | Ability to edit or reschedule events or appointments - only the ones that have been set by the owner of the event
177 | Live Classes |  |  | Ability to schedule live classes via a video conferencing platform
178 | Live Classes |  |  | Ability to host 2 way communication between teachers and students/batch of students
179 | Live Classes |  |  | Ability to manually add or remove participants from the class - only by the host
180 | Live Classes |  |  | Ability to add multiple hosts to the platform
181 | Live Classes |  |  | Ability to share screen, integrate smart screen, smart board for writing during live classes
182 | Live Classes |  |  | Integration of chat window to discuss during class
183 | Live Classes |  |  | Ability to run polls, realtime questions with the ability to choose the correct option, realtime live quiz exams, viva etc through the video platform
184 | Live Classes |  |  | Ability to record classes and save it along with the associated topic of the course
185 | Live Classes |  |  | Ability to schedule and reschedule live classes and tag it a particular course/module/submodule/topic etc.
186 | Live Classes |  |  | Ability to have personal interaction between student and teacher
187 | Live Classes |  |  | Ability to raise hand to ask a doubt or answer a question
188 | Live Classes |  |  | Ability to run live quiz sessions - student can answer questions in realtime and based on their performance realtime ranking will be calculated and displayed
189 | Live Classes |  |  | Ability to submit report during live class - report issues with class, lessons, inapropriate content, delivery quality, teacher delivery, offensive behaviour, spam, copyright issues etc
190 | Live Classes |  |  | Ability to take and add notes during live class - attached to particular time, or added as separate side note to each lecture
191 | Live Classes |  |  | Ability to divide a larger batch into breakout rooms to carry forward conversations
192 | Live Classes |  |  | Ability to share files, presentations during class
193 | Attendance |  |  | Ability to record attendace during live classes - both offline or online that will get recorded within the platform
194 | Attendance |  |  | Ability to show attendance report of each individual student in his dashboard - course wise
195 | Attendance |  |  | Ability to count attendance as a percentage towards the final grade for a course
196 | Attendance |  |  | Ability to count attendace via poll and tag it to a particular class
197 | Attendance |  |  | Ability to mark reason for attendance or late arrival - and keep a note of the reason
198 | Attendance |  |  | Ability to make attendace as a gradable item as part of a course or module
199 | Attendance |  |  | Ability to mark attendace individually or mark everyone present first and unmark the abseentees
200 | Attendance |  |  | Attendance module of the particular course will automatically show the students who are mapped to that course
201 | Attendance |  |  | Attendance will automatically take the current date and time, but there will also be provision to go back in time and edit any attendance data
202 | Attendance |  |  | Can mark student present, absent, debarred, late, informed leave, etc.
203 | Attendance |  |  | Run Attendance summary report attached to a particular course/batch
204 | Examination Module | Assignments |  | Ability to set Assignments as part of a Course/Module
205 | Examination Module | Assignments |  | Ability to mention weightage of each assessment as part of a course
206 | Examination Module | Assignments |  | Ability to create a group of Assignments under one single assessment
207 | Examination Module | Assignments |  | Ability to mention Assignment name and description (using text editor)
208 | Examination Module | Assignments |  | Ability to mention full marks to the questions, tasks, assignments, sub tasks
209 | Examination Module | Assignments |  | Ability to display marks as points, percentage, gpa etc.
210 | Examination Module | Assignments |  | Ability to allow solution submission to questions directly using text editor
211 | Examination Module | Assignments |  | Ability to submit solutions as File uploads, external links etc.
212 | Examination Module | Assignments |  | Ability to restrict type of file submissions allowed
213 | Examination Module | Assignments |  | Specify number of submissions or attempts allowed
214 | Examination Module | Assignments |  | Ability to set due dates to assignments
215 | Examination Module | Assignments |  | Ability to set availability dates or visibility dates of assignments
216 | Examination Module | Assignments |  | Ability to set assignment to individual students, group of students, batch, module or course level
217 | Examination Module | Assignments |  | Ability to assign assignment as a group assignment
218 | Examination Module | Assignments |  | Ability to Publish or Unpublish assignments
219 | Examination Module | Assignments |  | Ability to Save, Copy or Delete assignments
220 | Examination Module | Assignments |  | Ability to modify due dates or submission dates of assignments before any submission has been made
221 | Examination Module | Assignments |  | Ability to add a Rubrics or marking scheme to the assignment
222 | Examination Module | Assignments |  | Ability to peer-review and grade submissions
223 | Examination Module | Assignments |  | Ability to submit feedback to solutions or add auto-feedback
224 | Examination Module | Assignments |  | Ability to download submissions for marking
225 | Examination Module | Assignments |  | Ability to upload marked submissions with feedback
226 | Examination Module | Assignments |  | Ability to share assignments between Courses, Modules
227 | Examination Module | Assignments |  | Ability to view assignments before publishing
228 | Examination Module | Assignments |  | Ability to bulk update assignment due dates, availability dates, marking scheme, name etc as part of Edit Assignment option
229 | Examination Module | Assignments |  | All dates should run through proper validation e.g. invalid due dates, availability dates, lock unlock dates should be flagged
230 | Examination Module | Assignments |  | Ability to mark late submissions of assignments if submitted even 1 min late
231 | Examination Module | Assignments |  | Ability to create online assignments to submit assignments. Students can submit audio or video recordings by recording new media or uploading existing media
232 | Examination Module | Assignments |  | Files submissions can also be an annotated form of question paper uploaded by instructor
233 | Examination Module | Assignments |  | Students can also submit files through Google Drive, Google Aps LTI, Microsoft 365
234 | Examination Module | Assignments |  | Ability to include or exclude assignment submission as part of course final grade
235 | Examination Module | Assignments |  | Ability to mention instructor name who has marked the assignment or mention anonymous marking/annotation
236 | Examination Module | Assignments |  | Ability to enable assignments being graded by multiple instructors/reviewers
237 | Examination Module | Assignments |  | Ability to import SCORM files in an assignment
238 | Examination Module | Assignments |  | Ability to resubmit assignments multiple times before end time and end date - or allow only one submission
239 | Examination Module | Assignments |  | Ability to download all assignment submissions, grade it and bulk upload and each student individually sees the graded solution
240 | Examination Module | Assignments |  | Ability to creare a Peer reviewed assignment
241 | Examination Module | Quiz |  | Ability to set Quiz Exercises as part of the Modules
242 | Examination Module | Quiz |  | Quiz questions can be set from questions within Question Bank
243 | Examination Module | Quiz |  | Ability to mention weightage of each quiz
244 | Examination Module | Quiz |  | Ability to create a group of Quizzes under one single quiz
245 | Examination Module | Quiz |  | Ability to mention Quiz name and description (using text editor)
246 | Examination Module | Quiz |  | Ability to choose between graded or ungraded quiz or practice quiz
247 | Examination Module | Quiz |  | Ability to add Quiz to an already created Assignment as part of a Module
248 | Examination Module | Quiz |  | Ability to set time limit to a Quiz
249 | Examination Module | Quiz |  | Ability to specify number of attempts allowed for the quiz
250 | Examination Module | Quiz |  | Ability to view responses after submission, and whether correct or incorrect was done after it has been assessed
251 | Examination Module | Quiz |  | Ability to show correct answers on immediate submission, or after certain date has passed, or once marks/solution released
252 | Examination Module | Quiz |  | Ability to set availability dates or visibility dates of a quiz
253 | Examination Module | Quiz |  | Ability to set due dates to Quiz submissions or participation
254 | Examination Module | Quiz |  | Ability to shuffle questions/answers of a particular quiz
255 | Examination Module | Quiz |  | Ability to link quiz to a Question Bank from which questions can be pulled randomly or based on conditions
256 | Examination Module | Quiz |  | Ability to add Rubrics or Marking scheme for a quiz
257 | Examination Module | Quiz |  | Ability to edit a quiz before it has started/while it is running
258 | Examination Module | Quiz |  | Ability to Add questions to a quiz - MCQ, T/F, Fill in the blanks, Fill in multiple blanks, Multiple Answers, Matching, File Upload, Formula based question
259 | Examination Module | Quiz |  | Quiz can also be in the form of a Survey i.e. Ungraded quiz that can be shared with students
260 | Examination Module | Quiz |  | For Multiple Choice Questions - ability to set the possible answer choices and correct answer (in the backend)
261 | Examination Module | Quiz |  | For Multiple Choice Questions - ability to attach automated feedback to the choosen answer on submission
262 | Examination Module | Quiz |  | For True/False Questions - ability to set the possible answer choices and correct answer (in the backend)
263 | Examination Module | Quiz |  | For Fill in the Blanks Questions - ability to set the possible answer choices and correct answer (in the backend)
264 | Examination Module | Quiz |  | For Fill in the Blanks Questions - ability to show where the blank answer/multiple blank answers needs to be inputted
265 | Examination Module | Quiz |  | For Numerical Answer questions - ability to set the possible answer choices and the correct answer (some precision can be allowed)
266 | Examination Module | Quiz |  | Ability to set formula based questions e.g. What is 5+x?
267 | Examination Module | Quiz |  | Ability to preview a Quiz and quiz questions before publishing
268 | Examination Module | Quiz |  | Ability to participate in a preview quiz - showing start date, time elapsed, time remaining, submission time etc.
269 | Examination Module | Quiz |  | Ability to submit quiz and see solutions immediately or once released by teacher, and see marks immediately or once release by teacher
270 | Examination Module | Quiz |  | Protect a quiz with an access code to determine who is allowed to participate in the quiz
271 | Examination Module | Quiz |  | Show attempt history of a Quiz
272 | Examination Module | Quiz |  | Ability to restrict quiz submission after deadline has passed
273 | Examination Module | Quiz |  | Ability to view student progress of the quiz, number of attempts taken, time taken, marks scored etc
274 | Examination Module | Quiz |  | Ability to grant students extra attempts, grant extra time for timed quizzes, and manually unlock quiz attempts.
275 | Examination Module | Quiz |  | Ability to lock questions after answering.i.e. cannot return to the previous question once it has been answered.
276 | Examination Module | Quiz |  | Ability to send message to students who have not submitted the quiz
277 | Examination Module | Quiz |  | Ability to Lock quiz before deadline
278 | Examination Module | Quiz |  | Enable proctoring during Live Quiz or Assignments e.g. lockdown browser, face recognition etc.
279 | Examination Module | Quiz |  | Ability to regrade an assignment or quiz, once originally graded, published or released
280 | Examination Module | Quiz |  | Ability to Student View a created quiz and participate and submit a quiz as a dummy student
281 | Examination Module | Quiz |  | Ability to create Graded Quiz, Practice Quiz, Graded Survey, Ungraded Survey as the Quiz type when creating a new quiz
282 | Examination Module | Quiz |  | Ability to see correct answers immediately on submission of quiz, or solutions can be released later on
283 | Examination Module | Quiz |  | Ability to control when and for how long students can see the correct answers by setting dates
284 | Examination Module | Quiz |  | Quiz where multiple attempts are allowed will provide an option to store the highest score or average score or the latest score
285 | Examination Module | Quiz |  | Ability to lock questions once it has been answered i.e. students cannot navigate back to attempted questions
286 | Examination Module | Quiz |  | Ability to move back and forth between questions until Submit
287 | Examination Module | Quiz |  | Ability to Lock a quiz and set a unlock scheduled date (or manual unlock) so that students see the quiz date scheduled but can only participate once the unlock date arrives
288 | Examination Module | Quiz |  | Link a Question group / Question Bank to a Quiz from which questions can be pulled randomly for every participant
289 | Examination Module | Quiz |  | Ability to tag course content or sections of a course to a Quiz Question
290 | Examination Module | Quiz |  | Quiz statistics e.g. avg score, highest score, SD, percentage passed etc. and the ability to download these statistics
291 | Examination Module | Quiz |  | Ability to give extra attempts to students even after publishing a quiz
292 | Examination Module | Quiz |  | Ability to give extra time to a particular student, even after publishing a timed quiz
293 | Examination Module | Quiz |  | Ability to regrade an already graded quiz or question
294 | Examination Module | Exam Marking and Grading |  | Ability to view submitted assignment, tasks and comment on submissions and grade
295 | Examination Module | Exam Marking and Grading |  | Automatic grading of quiz questions when number of correct questions are determined
296 | Examination Module | Exam Marking and Grading |  | Ability to view submissions of individual student associated to an assignment or exam and give feedback and grade
297 | Examination Module | Exam Marking and Grading |  | An indication to show whether the assignment has been graded, ungraded, submitted, unsubmitted etc.
298 | Examination Module | Exam Marking and Grading |  | Ability to submit assignment solutions by sections
299 | Examination Module | Exam Marking and Grading |  | Ability to sort students by exam performance, date submitted, date graded etc other criteria
300 | Examination Module | Exam Marking and Grading |  | View the status of student submissions for a particular assignment/coursework e.g. Late, Unsubmitted etc.
301 | Examination Module | Exam Marking and Grading |  | Ability to update the status of the submission or status update happens automatically based on which stage of grading it is in
302 | Examination Module | Exam Marking and Grading |  | Ability to download submitted solutions and mark and upload for individual student
303 | Examination Module | Exam Marking and Grading |  | Ability to accept multiple solutions as file uploads or submissions as part of a single assignment
304 | Examination Module | Exam Marking and Grading |  | Ability to grade student submissions anonymously i.e. hide the name of student submitted
305 | Examination Module | Exam Marking and Grading |  | Ability to grade student submissions and publish them at one time only then it will be released and viewable to all students
306 | Examination Module | Exam Marking and Grading |  | Add annotated comments to student submissions
307 | Examination Module | Exam Marking and Grading |  | Ability to submit solutions as text entry to a question
308 | Examination Module | Exam Marking and Grading |  | Ability to grade text entry submissions
309 | Examination Module | Exam Marking and Grading |  | Ability to grade website url submissions, media submissions
310 | Examination Module | Exam Marking and Grading |  | Ability to re-send a submission back to student for re-submission with suggested corrections or modifications
311 | Examination Module | Exam Marking and Grading |  | Ability to integrate plagiarism detector to submissions
| Admin |  |  | Admin should have all the capabilities that a Teacher, Student, etc has | Subaccount can be the different Schools of the university -> then each school broken down to departments
Admin should be able to set and define the account structure of the platform - based on root account, sub-account,sub-sub-account structure
Admin of the root account will be the main admin, sub-accounts will have sub-admin with limited access rights
Admin should be able to map courses to account or sub-account - bulk upload or manually
Admin should be able to map teachers to the account or sub-account - bulk upload or manually
Admin should be able to map teachers to the course that he/she is supposed to teach - bulk upload or manually
Admin should be able to map courses to a term/semester based on university schedule - bulk upload or manually
Admin should be able to map students to account or subaccount - bulk upload or manually
Admin should be able to map students to courses for the particular term - bulk upload or manually
Admin should be able to filter courses by term or semester
|  |  |  | Each Account, Subaccount or Sub-Sub-account and so on can have corresponding admin rights with all the corresponding admin permissions and capabilities | E.g. admin of a sub-account will only see/modify courses, students of the particular sub-account
People added to Courses should have following roles - Teachers, Student, Observer, TA, Designer and their capabilities shall be defined accordingly
Admin should be able to set Course level and Account level role based permissions e.g. what a Teacher is capable of within a course, what a student is capable of within a course etc
Admin should be able to set Term/Semester dates, duration, start date end date, and who can access the term from when
Admin should be able to customize the theme of the platform i.e. add/change logo, layout colour, global font style etc.
Admin should have access to Analytics data

## Features created (hidden)
Module | Features
A
Dashboard
Client Information, Access Credentials & Access Permissions
Master Setup
Academic Structure
Users
Teachers
Students
Roles & Permissions
Classes
Subject
Batches
Exam Management

## Feedbacks (hidden)
Students don't receive email notifications sometime | Less useful for lab-based courses | Tools to make is easier to assess subjective paper for a large batch
Onboarding people is cumbersome | Student with less attendance also receive the notes | Should be able to copy/move content for a course from one semester to another
Faces problems in slow internet | Creating a rubric is not user-friendly | GeoTIFF file type should be supported
Too many features. Attendance is not that useful | Time consuming while adding/developing content | Discussion, Assignment, Syllabus sections should be improved
Collaboration is tough | Image formatting is difficult | Search bar in PDF reader
Login problems through mobile | Less storage space for multiple online submissions | Provision for Physics related diagram to be created
Proper training before directly jumping onto the interface of canvas | While online classes, the RHS panel shouldn't have too much content | Teacher should have an option to 'Lock/unlock' the file download option for students
The system is not contextual to teaching/learning in India | Include Add/delete option for courses | Mathematical expressions should be available
Limited choice for incorporation of learning tools | A panel for students who haven't submitted the assignments | Options like files and pages can be combined into one
Mobile app lacks lot of web features line student enrolment | Plagarism checker | There should be rules and template for Rubrics

## Arivoo Plan (Aug-Sep 2023) (hidden)
Feature (Admin) | Backend Progress | Done By | Start Date | End Date | Duration (Days) | Frontend Progress | Done By | Start Date | End Date | Duration (Days) | Designs (Aman)
Master Setup |  |  |  |  | 1 | Not Started | Avik Basak |  |  | 1 | Pending
User Management |  |  |  |  | 2 |  |  |  |  | 2
Admin Onboarding | In Progress |  |  |  | 0 | Done | Avik Basak | 2023-08-09 |  | 1 | Admin Onboarding
Teacher Onboarding | In Progress |  |  |  | 0 | Done | Avik Basak |  |  | 1 | Teacher Onboarding
Student Onboarding | In Progress |  |  |  | 0 | Done | Avik Basak |  |  | 1 | Student Onboarding
Admin opens other user's account | [5 empty] | Done | Avik Basak |  |  |  | Admin opens other user's Account
Admin opens Teacher's account | [5 empty] | Done | Avik Basak |  |  |  | Admin opens Teacher's account
Admin opens Student's account | [5 empty] | Done | Avik Basak |  |  |  | Admin opens Student's account
Admin opens his own profile | [10 empty] | Admin opens his own profile
Teacher opens his own profile | [10 empty] | Teacher opens his own profile
Student opens his own profile | [10 empty] | Student opens his own profile
Announcements | [10 empty] | Create Announcements
Role Management | Done | Avik Basak | 2023-08-07 | 2023-08-08 | 0.5 | Done | Avik Basak | 2023-08-07 | 2023-08-08 | 2 | Roles & Permissions
Program Management |  |  |  |  | 0.5 | Done | Avik Basak | 2023-08-03 | 2023-08-03 | 1 | Program Management
Course Management |  |  |  |  | 2
Add a New Course |  |  |  |  | 1 | [5 empty] | Add a New Course
Assign Teachers to a Course |  |  |  |  | 0.25 | [5 empty] | Assign Teachers to a Course
Course Templates | [5 empty] | Done | Avik Basak |  |  |  | Follow the same Flow acc. to previous theme
Enroll Students in a Course | [10 empty] | Enroll Students in a Course
Course Examination
Course Quizzes & Assignments
Announcements |  |  |  |  | 0.25 | [5 empty] | Announcements
Pages | [10 empty] | Pages
Settings | [10 empty] | Settings
Sections |  |  |  |  | 1 | [5 empty] | Sections
Course Content Management
Add Document | [10 empty] | Add Documents
Add Video | [10 empty] | Add Video
Add Web Urls | [10 empty] | Add Web Urls
Add Audio Files
Add Page | [10 empty] | Add Page
Add Quiz | [10 empty] | Follow the same Flow acc. to previous theme
Add Assignments | [10 empty] | Follow the same Flow acc. to previous theme
Add Examination | [9 empty] | 1 | Follow the same Flow acc. to previous theme
Exam Management
Question Bank | [10 empty] | Question Bank
Libraries | [10 empty] | Libraries
Exam Templates | [10 empty] | Exam Template (Non-Sectional Exam)
Exam Listing | [10 empty] | Exam Listing Page
Add Examination & Assign Questions | [10 empty] | Follow the same Flow acc. to previous theme
Add Questions
MCQ | [10 empty] | Follow the same Flow acc. to previous theme
Fill in the blanks | [10 empty] | Follow the same Flow acc. to previous theme
Match the following | [10 empty] | Follow the same Flow acc. to previous theme
True or False | [10 empty] | Follow the same Flow acc. to previous theme
Descriptive | [10 empty] | Follow the same Flow acc. to previous theme
Passage Based | [10 empty] | Follow the same Flow acc. to previous theme
Group Question | [10 empty] | Follow the same Flow acc. to previous theme
Term Management | [5 empty] | Done | Avik Basak | 2023-08-04 |  | 2
Creation | [5 empty] | Done | Avik Basak | 2023-08-04 | 2023-08-04 | 1
Assign Program & Courses | [5 empty] | Not Started |  |  |  |  | Assign Program & Courses in a Term
Routine Management
Routine Dashboard (Month, Week, Day, List) | [5 empty] | In Progress | Avik Basak | 2023-08-14 |  | 1 | Routine Dashboard (Month, Week, Day, List)
Add Routine | [5 empty] | Done | Avik Basak | 2023-08-16 |  |  | Add Routine (Repetitions ON)
Academic Structure Management | Done |  |  |  |  | Done | Avik Basak | 2023-08-16 | 2023-08-17
Login | [10 empty] | Login Screen
Dashboards
Admin
Teacher | [10 empty] | Teacher Dashboard
Student | [10 empty] | Student Dashboard
Holiday Listing | [10 empty] | Follow the same Flow acc. to previous theme
Feature (Teacher)
Dashboard | [10 empty] | Teacher Dashboard
Routine Management
Routines (Offline) | [10 empty] | Teacher Routines (Offline)
Routines (Online) | [10 empty] | Teacher Routines (Online)
Examinations
Listing Page | [10 empty] | Exam Listing Page
Exam opened to view Student List | [10 empty] | Exam Opened to View Student List
Mark Student's Exam | [10 empty] | Follow the same Flow acc. to previous theme
View Student Result | [10 empty] | Teacher Views Student's Result
Courses Assigned
Course Listing Page | [10 empty] | Assigned Courses List
Add Content in a Course | [10 empty] | Add Content in a Course
View Students in a Course | [10 empty] | View Students Section wise in a Course
Examinations | [10 empty] | Course Examinations
Quizzes & Assignments | [10 empty] | Course Quizzes & Assignments
Announcements | [10 empty] | Teacher Annoucements
Pages | [10 empty] | Pages
Settings | [10 empty] | Settings
Feature (Student)
Dashboard | [10 empty] | Student Dashboard
Live Announcement | [10 empty] | Live Announcement
My Courses
Course Listing Page (List & Card View) | [10 empty] | Course Listing Page (List & Card View)
Course Not Started by the student | [10 empty] | Course Not started by the student
No course items opened | [10 empty] | No Course item opened
Few Item Completed | [10 empty] | Few Items Completed
Course Completed | [10 empty] | Course Completed by the student
Pdf Opened by student | [10 empty] | PDF Opened
Video Opened | [10 empty] | Video Opened
Audio Opened | [10 empty] | Audio Opened
Webpage Opened | [10 empty] | Webpage Opened
Submit Assignment | [10 empty] | Submit Assignment
Page Opened | [10 empty] | Page Opened
My Examinations
All Exams (including Quizzes & Assignments) | [10 empty] | All Examinations
View Result | [10 empty] | View Result
Upload Assignment | [10 empty] | Upload Assignment
Start Quiz | [10 empty] | Follow the same Flow acc. to previous theme
Start Exam | [10 empty] | Follow the same Flow acc. to previous theme
My Routines
Offline Classes | [10 empty] | Offline Classes
Online Classes | [10 empty] | Online Classes
Email Template

## Project_Student (hidden)
Student SIde - Phase 1
Feature (Admin) | Dev Status | Dependecies / Comments | Dev | Est Time | Start Date | EndDate
Login | Not Completed fully | Validation is pending
Dashboard | Not Completed fully | Linking page links navigation pending
Live Announcement | Not Completed fully | Validation is pending
My Courses | Not Completed fully
Course Listing Page (List & Card View) | In progress | Card View is pending
Course Not Started by the student | Not Started | User status update SP is pending
No course items opened | Not Started
Few Item Completed | Not Started
Course Completed | Not Started
Course Indexing & Pagination | Not Started
Pdf Opened by student | Done
Video Opened | Done
Audio Opened | Done
Webpage Opened | Done
Submit Assignment | Done
Page Opened | Done
My Examinations | Done
All Exams (including Quizzes & Assignments) | Done
View Result | Done
Upload Assignment | Done
Start Quiz | Done
Start Exam | Done
My Routines | Not Completed fully
Offline Classes | Done
Online Classes | Not Started
Logout | Done
Profile | Done
Global Search | Not Devloped | Need PRD

## Project_Teacher (hidden)
Teacher SIde - Phase 1
Feature (Admin) | Dev Status | Dependecies / Comments | Dev | Est Time | Start Date | EndDate
Login | Not Completed fully | Validation is pending
Dashboard | Not Completed fully | Linking page links navigation pending
Routine Management | Not Completed fully
Routines (Offline) | Done
Routines (Online) | Not Started
Validation | Not Started
Examinations | Not Completed fully
Listing Page | Not Started | New UI needs to devloped
Exam opened to view Student List | Not Started | New UI needs to devloped
Mark Student's Exam | Not Started | New UI needs to devloped
View Student Result | Not Started | New UI needs to devloped
Courses Assigned | Not Completed fully
Course Listing Page | All items taken on Admin side
Add Content in a Course
View Students in a Course
Examinations
Quizzes & Assignments
Announcements
Pages
Settings
Validation | Not Started | Need PRD
Global Search | Not Devloped | Need PRD

## Sprint Calendar
SPRINT CALENDAR | [6 empty] | Click here - REGULAR RELEASE CALENDAR LINK
Sprint No. | Sprint Planning Date | Sprint Task Discussion | Sprint Start Date | Sprint End Date | Sprint Demo Date (T1) | Status | Rel No. | Date | Client
1 | 2023-07-14 | 2023-07-14 | 2023-07-17 | 2023-07-28 | 2023-07-28 | Completed
2 | 2023-07-28 | 2023-07-28 | 2023-07-31 | 2023-08-11 | 2023-08-11 | Completed
3 | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-25 | 2023-08-25 | Completed
4 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-09-08 | 2023-09-08 | Completed
5 | 2023-09-09 | 2023-09-09 | 2023-09-11 | 2023-09-22 | 2023-09-22 | Completed
6 | 2023-09-23 | 2023-09-23 | 2023-09-25 | 2023-10-06 | 2023-10-06 | Completed
7 | 2023-10-09 | 2023-10-09 | 2023-10-09 | 2023-10-20 | 2023-10-20 | Completed
8 | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-11-10 | 2023-11-10 | Completed
9 | 2023-11-20 | 2023-11-20 | 2023-11-20 | 2023-12-01 | 2023-12-01 | On going
10 | 2023-12-04 | 2023-12-04 | 2023-12-04 | 2023-12-15 | 2023-12-15 | Planned

## Resource Allocattion
Sprint 9 Resource Allocations
SPRINT 06 Resource Allocation |  |  |  | Sprint Working Days
Resource | Sprint Actual Velocity | Sprint Available Allocated | Utilized Velocity | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 | 2023-12-08
|  | Velocity | Velocity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Asfak Shaikh ( Mobile Dev) | 80
Neeraj Kumar (LMS Backend) | 80
Moupriya Das | 80
Arkya Santra | 80 | bar: 2023-11-27
Mousumi Dutta | 80
Smitha G S (QA) | 80
Soma Pal ( Support) | 64
Susmita Paul ( SMS Backend) | 40
Shilpa (Mobile Dev) | 80
Anjali (QA) | 20
Ankit ( UI/UX) | 40
ShubraJyoti (Product) | 80
Himanshu (Devops) | 20
Alok Ranjan (Project) | 20
SUM TOTAL | 844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Phase 2 (hidden)
User management | Custom/mandatory user profile fields | Fields at registration can be configured to be mandatory or optional. Additional fields can be added via an extension plugin.
User management | SSO (Single Sign On) | Third party authentication can be integrated with different type of providers such as SAML, OAuth 2.0 (Facebook, Google, Microsoft, LinkedIn, Github).
User management | Other authorization | Email and phone OTP based login, ID-password based authorization
Account management | Outcomes | Outcomes can be defined for an account
Account management | Rubric | Rubrics can be configures for an account
Account management | Grading | Grading can be defined for an account
Account management | Organization branding | Needs to be customised through main/top account. All child reflects the branding along their own account branding
Account management | Sub-account branding | Theme can be customized via changes in the templates and styles.
Account management | Custom branding | Custom domain (URL)
Course management | Guest access settings | Courses can partially be made available for guest access.
Course management | Invitation only | Courses can be configured to be invitation only.
Course management | Course prerequisites control | Course enrolment configuration based on successful completion of one or many courses
Course management | Self-enrollment capability | Learners can self-enroll to the courses (such as electives) that are configured.
Course management | Leaner activity tracking/monitor learner progress | Progress is monitored as measured by grades and by the completion of each of the course components.
Course management | Configure rubrics for manually graded exercises | Configurable rubrics are available for peer-graded and staff-graded exercises.
Course management | Import/export courses | Courses can be exported and imported from a native format (QTI).
Course management | Certificate management | Templates can be created and configured by organization and by language. Fields in the template can be overwritten per course.
Course management | Certificate management | Bulk generation of certificates
Course management | Certificate management | Revoke certificates
Course management | Certificate management | Certifications can be downloaded as pdf
Course management | Certificate management | Certifications can be easily shared in social networks
Course management | Wiki pages | Wiki pages can be used for articles, course outlines, FAQs, and information specific to the units and components.
Course management | Content restricted, based on dates | Each section or subsection in a course can be automatically published at a specific date in the future.
Course management | Course contents reusability | Course sections, subsections, and components can be easily duplicated and moved for re-use in other parts of the course. This saves time, since the content does not have to be re-built from scratch.
Course management | Author checklists for course readiness | Checklists help course staff ensure courses are fully ready before launching them.
Content management | Scorm and XAPI content support
Content management | LTI protocol (learning tools interoperability) | Platform should act as an LTI consumer and also as an LTI provider.
Exam management | Randomly pulling problems from a question bank. | Question banks to create randomized assessments within the courses.
Exam management | Annotation toll for assessing open-response questions | Annotation tool with rubric configuration should be available to assess an open-respose question
Exam management | Proctored exams | Using external tools and services, exams can be configured to be proctored.
Exam management | Exam process management | seating arrangement, admit card, exam enrollement, exam fee
Social learning tools | Polls in which the student can reply to a given question and then see the aggregated responses from the group | A poll component is available, with the option to either display or not display the aggregated responses to learners.
Social learning tools | Word cloud | Submit ideas or examples and have them listed in text walls, word clouds or similar visualizations
Social learning tools | Discussions forum | Course participants can engage in active discussions, which can be organized both as part of a course unit, and as course wide discussions. There are many configuration, management and moderation options for discussions.
Social learning tools | Student notes | Learners can add personal notes to specific course components. Student notes can be hidden/shown within a specific unit and also aggregated in a list with corresponding links.
Routine management | Attendance | Particitating user can mark their attendance during a live class.
Ticketing system | Chatbot | Chatbot integration to solve the user query
Video-conferencing | Video/audio streaming | Upto 150 participants
Video-conferencing | Whiteboard | To collaborate or to stream a file/video
Video-conferencing | Polls | To quiz and see leaderboard rank of a class
Video-conferencing | Comment | For textual interactions
Reports | Attendance
Reports | User enrolment
Reports | Course enrolment
Reports | Courses
Reports | Exam marks
Reports | Grading
Feedback | Survey creation/edit/delete

## Phase 3 (hidden)
User management | Self-registration capability | The platform can be configured for users to be able to register themselves.
User management | Integration to ERP | Fee payment and other user information can be fetched from ERP
User management | Act as user | Allows to browse the platform as one user
Course management | Survey enrollment (based on a response) | Courses can have entrance exams and be configured so that only learners who pass the exam are able to access the course.
Content management | Ecommerce | Ecommerce page can be created for courses
Exam management | Peer graded questions | Grading for open-response questions can be configured with a customizable rubric and can be performed by the learners themselves, other peers, the instructors, or any combination.
Social learning tools | bookmark course content | Learners can add personal bookmarks to specific course units. Bookmarks will be displayed in the specific unit and also aggregated in a list with the corresponding links.
Routine management | Automated routine | Baseed on the course, the assigned instructor and time slots, automated routine schedule can be created.
Ticketing system | Ticket creation/edit/delete | Users will be able to create tickets for support to based on their grievance
Ticketing system | Ticket assignment | Ticket can be autimatically assigned based on the issue or can manually assign to a support user.
Calendar and notification | Automated notification | Automated notification can be created for events course publishing, Class routine, exam notification etc.
Calendar and notification | Notificaition delivery system | Notifications can be delived on web, in mobile app as SMS or as an email.
Calendar and notification | Mass email | Mass email for an account or course users
Feedback | Feedback assignment

## Arivoo Product Backlog (hidden)
Phase 1 - Arivoo
Sl No. | Story ID | Sprint No. | Pending Features | Phase | Resource | User Story | Task | Hours required | Daily hour allocation | Working Date Allocation | Delivery Date(Expected) | Delivered Date | Delivery Status | PMO Remarks | Additional Comments
1 |  |  | Business | Phase 2 |  | 1. Bulk User Asign to course level
2 | [5 empty] | 2. Bulk Login Asgin
3
4
5

## Sprint 4 (hidden)
Sprint 4
Start Date : 25/09/2023(Monday)
End Date : 09/10/2023 (Friday)
Sprint Demo (Internal) : 09/10/2023 (Friday
Task Description | Backlog Module (EPIC) | Story ID | Client | Type | Responsible | Status | Est. hrs | Monday | Tuesday | Wednesday | Thursday | Friday | Monday | Tuesday | Wednesday | Thursday | Friday | Comment For Data Base Change In This task (To be given by Developer) | Demo Requirement | Over All Comments In Sprint retro & Demo
Admin Reports < UI + Dynamic Data> | Reports | NA | NA | New Req | Avik | Planned | 24
Teacher Reports < UI + Dynamic Data> | Reports | NA | NA | New Req | Avik | Planned | 16
Students Reports + Download + Dynamic Data | Reports | NA | NA | New Req | Avik | Planned | 8
Bug Fixes | Bug Fixes | NA | NA | New Req | Avik | Planned | 24
Setting Configuration | Setting | NA | NA | New Req | Satya | Planned | 8
Client Configuration | Client | NA | NA | New Req | Satya | Planned | 8
Reports SP | Reports | NA | NA | New Req | Satya | Planned | 8
Online class Integration | Online Class | NA | NA | New Req | Satya | Planned | 24
Course - Assignment | Course - Admin, Teacher | NA | LMS | New Req | Satya | Planned | 4
Course - Examination | Course - Admin, Teacher | NA | LMS | New Req | Satya | Planned | 4
Course - Announcement | Course - Admin, Teacher | NA | LMS | New Req | Satya | Planned | 4
Account - Announcement | Course - Admin | NA | LMS | New Req | Satya | Planned | 4
Contetn Managment - Quiz | Course - Admin | NA | LMS | New Req | Satya | Planned | 4
Contetn Managment - Assignment | Course - Admin | NA | LMS | New Req | Satya | Planned | 4
Student course progress | Course - Student | NA | LMS | New Req | Satya | Planned | 4
Content management - Student | Course - Student | NA | LMS | New Req | Satya | Planned | 4
QA Round 2 End to End | QA | NA | LMS | New Req | Smitha | Planned | 24
Bulk Upload < Logic> | Bulk Upload | NA | LMS | New Req | Shubrajyoti | Planned | 16
Validation PRD | Validation | NA | LMS | New Req | Shubrajyoti | Planned | 16
Design Review | Design | NA | LMS | New Req | Aman | Planned | 16
Reports Design Admin | Design | NA | LMS | New Req | Aman | Planned | 16
Setting Configuration | Setting | NA | NA | New Req | Avik | Planned | 8

## Current Sprint - Sprint 9
Sprint 9 (10 days)
Start Date : 13 Nov 2023 (Monday)
End Date : 24 Nov 2023 (Friday)
Sprint Demo (Internal) : 24, Nov 2023 (Friday)
[7 empty] | . | Date | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24
[8 empty] | Sprint day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task Description | Backlog Module (EPIC) | Story ID | Client | Type | Responsible | Status | Est. hrs | Taken Hrs | Monday | Tuesday | Wednesday | Thursday | Friday | Monday | Tuesday | Wednesday | Thursday | Friday | Comment For Data Base Change In This task (To be given by Developer) | Demo Requirement | Over All Comments In Sprint retro & Demo
Question bank integration with Rice LMS | Examination |  | RiceSmart | CR | Saumya | Done
Exam creation process automation from QB - automated library creation | Examination |  | RiceSmart | CR | Saumya | Done
MyActivity Analytics topic level and recommendation flow | Examination |  | RiceSmart | CR | Saumya | Done
Based on weakness or questions mistaken - give recommended exams/quiz - post recommendation analytics | Examination |  | RiceSmart | CR | Saumya | Done
Recommending content based on exam performance | Examination |  | RiceSmart | CR | Saumya | Done
Create a self-exam practice feature - based on student preferred parameters - e.g. no. of questions, difficulty level, which course, subject, topic .. | Examination |  | RiceSmart | CR | Saumya | Done
Offline Attendance - Teacher | Attendance |  | RiceSmart | CR | Neeraj | In Progress
Offline Attendance - Student | Attendance |  | RiceSmart | CR | Neeraj | In Progress
Poll Live class (Zoom) | Zoom |  | RiceSmart | CR | Himanshnu | Planned
Load Testing on RICE Server optimisation | Examination |  | RiceSmart | CR | Himanshnu | Planned
EXAM API Optimisation | Examination |  | RiceSmart | CR | Saumya | Planned
Exam API Load Test | Examination |  | RiceSmart | CR | Alok | Planned
WAF- Implementation on RICE | Server/ API |  | RiceSmart | CR | Himanshnu | Planned
WAF - API Optimisation | WAF |  | RiceSmart | CR | Neeraj | Planned
BUG FIXES:Report: 1.Exam marks report >> By selecting the exam only that batch assigned to the exam should be listed (not all the batches of that course ) 2.All reports >> By default should not select any exam state and exam list (Existing bug ) 3.Report tittle name should be changed in the Report List (Existing bug ) the teacher is present but still in teacher report its showing absent 5.Sorting icon in reports table was displaying in dev server but not in pp 6.Attendance report >> For teacher login we are not getting any data for student attendance report 7.Attendance report >> Teacher attendance is also displaying in student report 8.Attendance report >>If no data is their the graph should not display (for teacher login) | Reports |  | RiceSmart | CR | Neeraj | In Progress
o Online Classes Attendance Log (Student Report list) | Reports |  | RiceSmart | CR | Neeraj | Done
o Advance Teacher Utilization Report | Reports |  | RiceSmart | CR | Neeraj | In Progress
o Teacher Attendance Reports | Reports |  | RiceSmart | CR | Neeraj | In Progress
Quiz bug list : 1.After submitting quiz exam its refreshing all data 2.Should display unlocked date as routine completed date not the date of exam created 3.Search invalid char and apply filter >> it should not display error message with exam card 4.If the user is defaulter should not get quiz exam 5.Free user course should not list in course dropdown (demo ) 6.while loading the page should not display exam card 7.Should not display the quiz data if batch is expired 8.If there is no quiz should display no data available message section wise also | Reports |  | RiceSmart | CR | Neeraj | In Progress
System configuration & code setup | System |  | RiceSmart |  | Himanshnu | Planned
Sprint Call / Adhoc Meetings | Meetings |  | RiceSmart |  | Neeraj | In Progress | 6
Sprint Call / Adhoc Meetings | Meetings |  | RiceSmart |  | Shubrajyoti | In Progress | 6
Sprint Call / Adhoc Meetings | Meetings |  | RiceSmart |  | Asfak | In Progress | 10 | bar: 1 to 10
QA on PROD APK / PP APK for 3.3.4 | QA |  | RiceSmart |  | Smitha | Done | 12
QA ON Reports | QA |  | RiceSmart |  | Smitha | In Progress | 12
QA ON Quizz | QA |  | RiceSmart |  | Smitha | In Progress | 12
Regression QA | QA |  | RiceSmart |  | Smitha | Planned | 12
QA on SMS | QA |  | RiceSmart |  | Smitha | Planned | 12
1. Coupon API changes : one plan multi product | Ecom-SMS |  | RiceSmart |  | Susmita | Planned | 4
2. For "One Plan- multiple product" : Coupons needs to display for all products. (New CR) | Ecom-SMS |  | RiceSmart |  | Susmita | Planned | 4
3. CA ROLE IMPLEMENTATION ON SMS | CA |  | RiceSmart |  | Susmita | Planned | 4
4. New Ecom Admin Walkthrough | Walkthrough |  | RiceSmart |  | Susmita | Planned | 4
5.Cyclic Admission walkthrough | Walkthrough |  | RiceSmart |  | Susmita | Planned | 4
PP Deployement / Prod Deployement | DevOps |  | RiceSmart |  | Himanshnu | Planned
QA on Exam - Quizz Automated question Bank | Examination |  | RiceSmart |  | Smitha | Planned
New Dispatch scheme | SMS |  | RiceSmart |  | Susmita | Planned | 4
QA Sanity on Prod / PP | QA |  | RiceSmart |  | Anjali | Planned | 20
EXAM OFF LINE PRD | Product |  | RiceSmart |  | Shubrajyoti | Planned
Client meeting | Product |  | RiceSmart |  | Shubrajyoti | Planned
One product - Multiple Plans / Course Ecom flow | APK |  | RiceSmart | CR | Asfak | In Progress | 14 |  | 1: 7; 2: 7
Offline Attendance - Student | APK |  | RiceSmart | CR | Shilpa (Asfak) | In Progress | 12 |  | 1: 4; 2: 4; 3: 4
Sprint Call / Adhoc Meetings | Meetings |  | RiceSmart | Meeting | Smitha | In Progress | 10
Sprint Call / Adhoc Meetings | Meetings |  | RiceSmart | Meeting | Himanshnu | In Progress | 10
Sprint Call / Adhoc Meetings | Meetings |  | RiceSmart | Meeting | Susmita | In Progress | 10 |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Quizz UI bugs | Quiz |  | RiceSmart | CR | arkya | In Progress | 5
Teacher Attendance Reports | Reports |  | RiceSmart | CR | arkya | In Progress | 12 |  | 1: 6
Advance Teacher Utilization Report | Reports |  | RiceSmart | CR | arkya | In Progress | 12
Batchwise Attendance Summary Report | Reports |  | RiceSmart | CR | moupriya | In Progress | 8 |  | 1: 6
Online Classes Attendance Log (Student Report list) | Reports |  | RiceSmart | CR | moupriya | In Progress | 12
OpenEDX Setup | Setup |  | RiceSmart | project setup | mousumi | In Progress | 8 |  | 1: 6; 2: 2
Ricesmart configration + databased setup (DEV database setup) | Setup |  | RiceSmart | project setup | mousumi | In Progress | 4 |  | 2: 4
Flutter - local storage, preference | Flutter |  | Flutter |  | Shilpa (Asfak) | In Progress | 12 |  | 1: 4; 2: 4; 3: 4
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Validate Coupon API Modify for Multiple Product and one Plan | SMS |  | RiceSmart |  | Susmita |  |  |  | 6: 4
Valid Coupon Fetch API Modify For Multiple Product One Plan | SMS |  | RiceSmart |  | Susmita |  |  |  | 6: 2
Additional field in PreEnquiry_SMS | [8 empty] | 7: 6; 10: 2.4
API discussion | SMS |  | RiceSmart |  | Susmita | bar: 7
Cron Job Issue | SMS |  | RICE |  | Susmita |  |  |  | 8: 2.5; 9: 1
Issue of school Support | SMS |  | AIS |  | Susmita | bar: 8
Additional field in PreEnquiry_SMS with Report | [8 empty] | 10: 2.4
Rice Deeplinking issue Resolve + hide social binding | APK |  | RICE | CR | Asfak | DONE | 4
Note on M17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: LogBook Discussion

## Sprint 10
Sprint 10 (10 days)
Start Date : 27 Nov 2023 (Monday)
End Date : 04,Dec 2023 (Friday)
Sprint Demo (Internal) : 04, Dec 2023 (Monday)
[7 empty] | . | Date | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 | 2023-12-08 | 2023-12-11 | 2023-12-12 | 2023-12-13 | 2023-12-14 | 2023-12-15
[8 empty] | Sprint day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task Description | Backlog Module (EPIC) | Story ID | Client | Type | Responsible | Status | Est. hrs | Taken Hrs | Monday | Tuesday | Wednesday | Thursday | Friday | Monday | Tuesday | Wednesday | Thursday | Friday | Comment For Data Base Change In This task (To be given by Developer) | Demo Requirement | Over All Comments In Sprint retro & Demo
LMS API Needs to be - WAF implementaion | LMS |  | RiceSmart | CR | Neeraj | Planned
Exam notification end to end | Notification |  | RiceSmart |  | Neeraj | Planned
Deafulter Mo engage notification | Notification |  | RiceSmart |  | Neeraj | Planned
Additional field in ACAdmission Report in SSRS 1. Study The work of SSRS adding new Field 2.Impliments | SSRS Report |  | RICE |  | Susmita | In Progress | 16 |  | 3: 3.5
Valid Coupon Fetch API Modify For Multiple Product One Plan | Coupon API |  | RiceSmart |  | Susmita | Done | 7 | 7 | 2: 7
Additional field in PreEnquiry_SMS | Deplyment |  | RICE |  | Susmita | Done | 1 | 1 | bar: 1
New Dispatch (504,526) |  |  | RICE |  | Susmita | Done |  |  | 3: 1.7
huddle meeting |  |  | RiceSmart |  | Susmita | In Progress |  |  | 3: 0.9
Discussion with app team for api |  |  | RiceSmart |  | Susmita | In Progress |  |  | 3: 0.7
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned
Planned